## Contractor A
Contractor: | Contractor A
|  |  | Number of Issues: | 5 | 1 | 1 |  |  | Number of Issues: |  | 3
JOB NUM | LAST NAME | Date | Unit Type | WX | Davis-Bacon | Contract | Measure | Observation | Recommendation | Date Notified | Action Required | Date Returned | N/A | N/A |  | WX | Davis-Bacon | Contract | Action Required
11111 | EXAMPLE | 2010-02-02 | HOUSE |  | X |  | n/a | Resubmit Payroll 3 - Hours do not match addendum | N/A | 2010-02-12 | YES | 2010-03-15 | APARTMENT | YES
12616 | Kohn | 2010-02-24 | HOUSE | X |  |  |  | missing measures | complete wx measures | 2010-03-01 | YES | 2010-03-02 | CONDO | NO |  | 1 | 0 | 0 | 1
12654 | Oakes | 2010-01-28 | RENTAL UNIT | X |  |  | n/a | incorrect billing | invoice for measures completed | 2010-02-07 |  |  | DUPLEX |  |  | 1 | 0 | 0 | 0
|  | 2010-02-01 | N/A |  | X |  |  | Payrolls must come current | Submit payrolls to be current | 2010-02-05 | YES | 2010-02-10 | HOUSE |  |  | 0 | 1 | 0 | 1
|  | 2010-01-25 | N/A | X |  | X |  | David Jones-Need lead safe certificate | None | 2010-02-01 | YES | 2010-02-05 | MOBILE HOME |  |  | 1 | 0 | 1 | 1
12718 | Stribling | 2010-03-17 | MOBILE HOME | X |  |  | Foundation | Insulation installed wrong | Remove paperbacking from insul. | 2010-03-22 | NO |  | MULTI-UNIT 2-4 |  |  | 1 | 0 | 0 | 0
13111 | Johnson | 2010-07-09 | HOUSE | X |  |  | n/a | Contractor left material waste on client's driveway pictures included in file | post clean-up | 2010-04-10 | NO | 2010-05-20 | MULTI-UNIT 5+ |  |  | 1 | 0 | 0 | 0
[13 empty] | RENTAL UNIT |  |  | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[15 empty] | Totals | 5 | 1 | 1 | 3

## Contractor B
Contractor: | Contractor B
|  |  | Number of Issues: | 3 | 2 | 0 |  |  | Number of Issues: |  | 4
JOB NUM | LAST NAME | Date | Unit Type | WX | Davis-Bacon | Contract | Measure | Observation | Recommendation | Date Notified | Action Required | Date Returned | N/A | N/A |  | WX | Davis-Bacon | Contract | Action Required
11111 | EXAMPLE | 2010-02-02 | HOUSE |  | X |  | n/a | Resubmit Payroll 3 - Hours do not match addendum | N/A | 2010-02-12 | YES |  | APARTMENT | YES
25456 | Conrad | 2010-04-15 | HOUSE | X |  |  | Rework | Rework-needs additional insulation in attic | complete wx measures | 2010-04-15 | YES | 2010-04-20 | CONDO | NO |  | 1 | 0 | 0 | 1
|  | 2010-04-17 |  |  | X |  |  | Mark Davis-Employee is not authorized to work | Background Check | 2010-04-17 | YES | 2010-04-25 | DUPLEX |  |  | 0 | 1 | 0 | 1
74560 | Mitchell | 2010-04-19 | MOBILE HOME | X |  |  | Rework | Rework-bathroom exhaust fan not working | replace exhaust fan | 2010-04-19 | YES | 2010-04-22 | HOUSE |  |  | 1 | 0 | 0 | 1
56952 | Hill | 2010-04-25 | MOBILE HOME | X |  |  | Insulation | Insulation exposed, needs repair | repair belly insulation | 2010-04-25 | YES | 2010-04-30 | MOBILE HOME |  |  | 1 | 0 | 0 | 1
69988 | Miller | 2010-04-27 | RENTAL UNIT |  | X |  | Payroll | Missing Payroll for this job | Need payroll for this job | 2010-04-27 |  |  | MULTI-UNIT 2-4 |  |  | 0 | 1 | 0 | 0
[13 empty] | MULTI-UNIT 5+ |  |  | 0 | 0 | 0 | 0
[13 empty] | RENTAL UNIT |  |  | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[15 empty] | Totals | 3 | 2 | 0 | 4

## Contractor C
Contractor: | Contractor C
|  |  | Number of Issues: | 3 | 2 | 0 |  |  | Number of Issues: |  | 5
JOB NUM | LAST NAME | Date | Unit Type | WX | Davis-Bacon | Contract | Measure | Observation | Recommendation | Date Notified | Action Required | Date Returned | N/A | N/A |  | WX | Davis-Bacon | Contract | Action Required
11111 | EXAMPLE | 2010-02-02 | HOUSE |  | X |  | n/a | Resubmit Payroll 3 - Hours do not match addendum | N/A | 2010-02-12 | YES |  | APARTMENT | YES
|  | 2010-02-15 |  |  | X |  | Payroll | Payroll 7,8,9 week ending dates do not match payroll records | Resubmit Payrolls 7,8,9 | 2010-02-15 | YES | 2010-02-22 | CONDO | NO |  | 0 | 1 | 0 | 1
85452 | Duane | 2010-03-10 | HOUSE | X |  |  | Thermostat | Return and install thermostat | Rework | 2010-03-10 | YES | 2010-03-15 | DUPLEX |  |  | 1 | 0 | 0 | 1
58965 | Markman | 2010-04-15 | MOBILE HOME | X |  |  | Permit | Copy of permit needed on installed furnace | Permit | 2010-04-16 | YES | 2010-05-01 | HOUSE |  |  | 1 | 0 | 0 | 1
63225 | Goodman | 2010-05-01 | CONDO | X |  |  | Weatherstrip | Weatherstrip needs to be installed in attic access | Weatherstriping | 2010-05-02 | YES | 2010-05-10 | MOBILE HOME |  |  | 1 | 0 | 0 | 1
|  | 2010-05-15 |  |  | X |  | Payroll | Need authorized for Steve Tompson, child support deduction | Deduction Authorization | 2010-05-15 | YES | 2010-05-17 | MULTI-UNIT 2-4 |  |  | 0 | 1 | 0 | 1
[13 empty] | MULTI-UNIT 5+ |  |  | 0 | 0 | 0 | 0
[13 empty] | RENTAL UNIT |  |  | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[15 empty] | Totals | 3 | 2 | 0 | 5

## Summary All Contractors
Summary of All Contractors
Contractor | WX | Davis-Bacon | Contract | Action Required
Contractor A | 5 | 1 | 1 | 3
Contractor B | 3 | 2 | 0 | 4
Contractor C | 3 | 2 | 0 | 5