## Federal Fiscal Year
State Management Calendar for Reporting Year October 2017-September 2018
| Quarter I |  |  | Quarter II |  |  | Quarter III |  |  | Quarter IV
CSBG Activity | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER
State Plan Development | Quarter II MARCH: Begin to discuss State Plan input with network; Quarter III APRIL: Begin drafting plan; Quarter III MAY: Get input from network: discussions/meetings with Eligible Entities. Integrate ACSI results. Hold public or legislative hearing; Quarter IV JULY: Hold public or legislative hearing; Quarter IV AUGUST: Secure apprpriate signatures from State Office; Quarter IV SEPTEMBER: State Plan due on Sept. 1st to HHS via OLDC
CSBG Annual Report/IS Survey | Quarter I OCTOBER: Send IS to Eligible Entitites; Quarter II JANUARY: IS data due to State Office from Eligible Entities; Quarter II FEBRUARY: Review IS data; Quarter II MARCH: IS Survey due to NASCSP 3/31; Quarter III APRIL: Review data memos and send back final data base to NASCSP
Organizational Standards | Quarter I NOVEMBER: Revise/Update Standards assessment tools for Eligible Entities (if necessary); Quarter II MARCH: Report on results of assessments in Annual Report, Module 1.; Quarter IV JULY: Ongoing assessment of Organizational Standards
Eligible Entity Community Action Plan/Contract | Quarter II MARCH: Work on revisions in contract/CAP, if necessary; Quarter III APRIL: Work on revisions in contract/CAP, if necessary; Quarter III MAY: Get input from network: discussions/meetings with Eligible Entities; Quarter III JUNE: Send contracts/CAP to Eligible Entities for completion; Quarter IV JULY: Send contracts/CAP to Eligible Entities for completion; Quarter IV AUGUST: Review contracts/CAP; executed contracts in place for 9/30
Monitoring | Quarter IV JULY: Review monitoring tools; Quarter IV SEPTEMBER: Release monitoring schedules/ tools to network
RPIC T/TA Plan | Quarter I OCTOBER: Final T/TA Plan submitted to OCS 10/1; Quarter IV JULY: Meet with State Association to collaborate on T/TA Plan for next year
American Customer Satisfaction Survey (ACSI) | Quarter I OCTOBER: Review of the ACSI results; Quarter I NOVEMBER: Share results with network; Quarter I DECEMBER: Ongoing communication with network; Quarter II JANUARY: Ongoing communication with network; Quarter III APRIL: Ongoing communication with network; Quarter IV JULY: Ongoing communication with network
Professional Development | Quarter II JANUARY: CAP MLTC; Quarter II FEBRUARY: NASCSP Conference; Quarter III JUNE: CAPLAW Conference; Quarter IV AUGUST: CAP Convention; Quarter IV SEPTEMBER: NASCSP Annual Conference

## Calendar Year
State Management Calendar for Reporting Year January 2017-December 2018
| Quarter I |  |  | Quarter II |  |  | Quarter III |  |  | Quarter IV
CSBG Activity | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
State Plan Development | Quarter I MARCH: Discuss State Plan input with network; Quarter II APRIL: Draft State Plan; Quarter II MAY: Get input from network: discussions/meetings with Eligible Entities. Integrate ACSI results. Hold public or legislative hearing; Quarter III JULY: Hold public or legislative hearing; Quarter III AUGUST: Secure apprpriate signatures from State Office; Quarter III SEPTEMBER: State Plan due on Sept. 1st to HHS via OLDC
CSBG Annual Report/IS Survey | Quarter I JANUARY: IS data due to State Office from Eligible Entities; Quarter I FEBRUARY: Review IS data; Quarter I MARCH: IS Survey due to NASCSP 3/31; Quarter II APRIL: Review data memos and send back final data base to NASCSP; Quarter IV OCTOBER: Send next year's IS/AR forms to Eligible Entitites
Organizational Standards | Quarter I JANUARY: Revise/Update Standards assessment tools for Eligible Entities (if necessary); Quarter I MARCH: Report on results of assessments in Annual Report, Module 1.; Quarter III JULY: Ongoing assessment of Organizational Standards; Quarter IV NOVEMBER: Revise/Update Standards assessment tools for Eligible Entities (if necessary)
Eligible Entity Community Action Plan/Contract | Quarter I MARCH: Work on revisions in contract/CAP, if necessary; Quarter II APRIL: Work on revisions in contract/CAP, if necessary; Quarter II MAY: Get input from network: discussions/meetings with Eligible Entities; Quarter II JUNE: Send contracts/CAP to Eligible Entities for completion; Quarter III JULY: Send contracts/CAP to Eligible Entities for completion; Quarter III AUGUST: Review contracts/CAP; executed contracts in place for 9/30
Monitoring | Quarter III JULY: Review monitoring tools; Quarter III SEPTEMBER: Release monitoring schedules/ tools to network
RPIC T/TA Plan | Quarter III JULY: Meet with State Association to collaborate on T/TA Plan; Quarter IV OCTOBER: Final T/TA Plan submitted to OCS 10/1
American Customer Satisfaction Survey (ACSI) | Quarter I JANUARY: Ongoing communication with network; Quarter II APRIL: Ongoing communication with network; Quarter III JULY: Ongoing communication with network; Quarter IV OCTOBER: Review of the ACSI results; Quarter IV NOVEMBER: Share results with network; Quarter IV DECEMBER: Ongoing communication with network
Professional Development | Quarter I JANUARY: CAP MLTC; Quarter I FEBRUARY: NASCSP Conference; Quarter II JUNE: CAPLAW Conference; Quarter III AUGUST: CAP Convention; Quarter III SEPTEMBER: NASCSP Annual Conference

## July Year
State Management Calendar for Reporting Year July 2017-June 2018
| Quarter I |  |  | Quarter II |  |  | Quarter III |  |  | Quarter IV
CSBG Activity | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
State Plan Development | Quarter I JULY: Hold public or legislative hearing; Quarter I AUGUST: Secure apprpriate signatures from State Office; Quarter I SEPTEMBER: State Plan due on Sept. 1st to HHS via OLDC; Quarter III MARCH: Begin to discuss next year's State Plan input with network; Quarter IV APRIL: Begin drafting plan; Quarter IV MAY: Get input from network: discussions/meetings with Eligible Entities. Integrate ACSI results. Hold public or legislative hearing
CSBG Annual Report/IS Survey | Quarter II OCTOBER: Send IS to Eligible Entitites; Quarter III JANUARY: IS data due to State Office from Eligible Entities; Quarter III FEBRUARY: Review IS data; Quarter III MARCH: IS Survey due to NASCSP 3/31; Quarter IV APRIL: Review data memos and send back final data base to NASCSP
Organizational Standards | Quarter I JULY: Ongoing assessment of Organizational Standards; Quarter II NOVEMBER: Revise/Update Standards assessment tools for Eligible Entities (if necessary); Quarter III MARCH: Report on results of assessments in Annual Report, Module 1.
Eligible Entity Community Action Plan/Contract | Quarter I JULY: Send contracts/CAP to Eligible Entities for completion; Quarter I AUGUST: Review contracts/CAP; executed contracts in place for 9/30; Quarter III MARCH: Work on revisions in contract/CAP, if necessary; Quarter IV APRIL: Work on revisions in contract/CAP, if necessary; Quarter IV MAY: Get input from network: discussions/meetings with Eligible Entities; Quarter IV JUNE: Send contracts/CAP to Eligible Entities for completion
Monitoring | Quarter I JULY: Review monitoring tools; Quarter I SEPTEMBER: Release monitoring schedules/ tools to network
RPIC T/TA Plan | Quarter I JULY: Meet with State Association to collaborate on T/TA Plan for next year; Quarter II OCTOBER: Final T/TA Plan submitted to OCS 10/1
American Customer Satisfaction Survey (ACSI) | Quarter I JULY: Ongoing communication with network; Quarter II OCTOBER: Review of the ACSI results; Quarter II NOVEMBER: Share results with network; Quarter II DECEMBER: Ongoing communication with network; Quarter III JANUARY: Ongoing communication with network; Quarter IV APRIL: Ongoing communication with network
Professional Development | Quarter I AUGUST: CAP Convention; Quarter I SEPTEMBER: NASCSP Annual Conference; Quarter III JANUARY: CAP MLTC; Quarter III FEBRUARY: NASCSP Conference; Quarter IV JUNE: CAPLAW Conference