WA Low Income Weatherization COVID Risk Assessment: Initial Observations

WSU Energy Program

4/29/2020

Who Did We Talk To

- Large Budget  Urban:  Clark  KCHA  ,  Pierce

- Moderate Budget  Urban:  OPPCO, CAC LMT, OIC

- Moderate Budget  Rural:  Coastal

- Small Budget Rural:  HopeSource

- Tribal:  SIHA  and YNHA

Observations

- Initial contacts are heavily weighted toward urban and moderate budget agencies.  Need to include a few more smaller agencies

- Peer group reps are representing peer groups.

- Commerce doesn’t have systematic info on which agencies are most at risk

- Action Item:  Need to do a quick survey or check in

General Situation

- Urban  agencies have enough slack and alternate funding sources to make it 3-4 months without providing in-home services.

  - CAPS  with  PPE loans have a lot more flexibility than those that don’t

  - A key concern is burning through support and flexible match (MM and LIHEAP and to a lesser extent BPA) so there isn’t funding  to match or wrap around utility $  (which may not be as flexible).   This issue is a bigger deal to agencies with bigger utility match (OPPCO 2;1, CAC LMT 1:1 etc).

    - Action item:  Should there be outreach to PSE Avista etc to get temporary COVID response flexibility for increased support costs.

- Smaller agencies  or those with larger crews (and no alternatives) are  closer to the edge

  - Hopesource has a 4-6 weeks before things get complicated(1-2 months out).  Som

  - Coastal has temporarily closed Wx program and laid off staff

  - YNHA has laid off wx but do expect them to return to Wx vacant units.  Audit staff reduced to part time

  - SIPA has 1-2 months of work on vacant (or relocated) units

- Contractors have largely responded by laying off or furloughing staff

  - Varying levels of contact and communication with contractors

  - Larger contractors (Richart) are in good contact – and generally willing to do what it takes to do the work

  - Less is known about smaller (Plumbers etc)

  - Lots of protocols floating around

  - Not a lot of systemic info on how or when they will come back and whether they have what they need to meet Governor’s guidance

    - Do we want to interview contractors -  what would we ask

Returning to Work

- Common expectation is return to service will be slow and ramped up with “lower” risk projects done first.

  - Three models put forward:

    - Agencies that can or have to start slowly with lowest risk projects (vacant, simple, non vulnerable)

      - A key constraint for returning to service for agencies is PPE.  Most have agencies limited inventories (1 month or less) staff to conduct Pre/Audit/QA   Many gave away supplies to  health care providers … and have re-ordered – but have no read on when they will get supplies

    - A few agencies pilot by developing  and testing protocols  and tools.

    - Build the pipeline – figure out how to get staff in the field

- Perception of level of risk and risk tolerance vary greatly including

  - degree and complexity of required changes

  - degree changes will effect cost varies from + 15-20% to + 100%

  - what they need to start up

    - Some agencies are looking for a “clear to proceed” signal from Commerce

    - Or at least guidance on what they should have in place

    - A return to work order and guidelines specifically for weatherization or  in home contracting and repair services in occupied dwelling  (higher risk  or general construction).

- Contractor capacity is huge issue and unknown

  - Contractors have been eager partners for the most part and have proposed protocols

    - How much is enough  - what is a good disinfecting protocol

    - What specifically is needed for managing client contacts exposure in the homes

  - How do you enforce requirements with contractors

    - Do you need new language in contracts?

    - How do new  requirements get priced?

    - Do they get enforced?   How are they assured?

  - Significant new coordination and scheduling work and client communications work

  - Workforce issues are not likely to an issue anytime soon (as ramp up will be slow)

- The Stay in Office policy has resulted in several major improvement to processes and has accelerated transition to electronic storage and electronic records systems and several improvements to processes

  - Need to capture them

Risk Analysis

- Lots of help in putting together the risk map

- Comprehensive but a bit daunting

  - And not as accessible or easy to use

- There are a very long list is issues and mitigation strategies

  - Commerce has limited capacity and can’t address all of them (and may not be the best entity to do it?

  - Intake and office management issues seem to be generally in good shape and lower risk?

    - The exception is risk triage  and client communications

  - Audit related risks and protocols (and PPE) are a near term need  -- as this is needed for start up

  - Contractor protocols are a bigger need – but there may be more time to address.