## Sheet1
Stage | Issue | Risk Level | Mitigation Strategies | Cost Impact | Change Action Required | Other Issues | Priority to Pursue | Who Leads | Target Date | Commerce Action Needed
All Stages | Client Communications – Expectations and New Processes Risk Awareness | Moderate | Education on What Agencies are doing? What are the COVIDS risks and how managed | Low - moderate | Updating web-sites? Client hand outs?
|  |  | New client expectations? Changes in Process and Priorities | Low moderate | Client intake scripts?
|  |  | Comprehensive Client Communication Plan | ??? | ID where changes to processes and protocols need to made | Encouraged vs required communications
All Stages | Harmonization of Guidance - Communication of requirements | Moderate | Review and align guidance – cross index requirements – best practice. | Moderate | Cross index (x requirement/y desired in z guidance)
|  |  | Compile guidance and post | Low | Review for quality and relevance | Location - who curates
|  |  | Commerce Interpretation of Govs Guidance | ?? | What does commerce need to fund? How to interpret key guidance? | How to navigate guidance vs approving plans? When will Commerce reimburse for in home services?
|  |  | Use of temporary guidance memo – rather than formal policy manual updates | Low | Commerce process | What to keep and preserve - when to transistion to official policy Tracking
|  |  | Rapid review | Low | System for sharing draft guidance
|  |  | Sunset / renewal provisions (increase acceptance0 | Low | Language qnd timing | Concern temporary requirements become permanent
|  |  | Clear articulation of guidance roles | Low | Place – person to harmonize | fit with existing systems PDC TDC
|  |  | Best practice standards | Moderate
All Stages | Liability for COVID – Adverse Outcomes | High | Governor’s Guidance – Restrictions Lifted | No control | Monitor - request specific guidance | May not get specific lifting - what counts
|  |  | Commerce Guidance - What needs to be in place? Plans? Policies? Training? | ?? | Check with AG --- what is Commerce's risk tolerance. | Conflicting guidance
|  |  | Contractor Liability - Responsibility | ?? | Draft language - set up process | Impact on contractor retention
|  |  | Additional Client Communication - Liability Waiver | Low | Draft language - set up process | Legal review
All Stages | Access to PPE | High | Identify – quantify need | Low | Inventory current stocks Cost survey
|  |  | Critical (medical/n95) vs lower levels (cloth) | Low | Review process for risk | Link to guidance and protocols
|  |  | Train on appropriate use and type | Moderate | Develop and delivered training | Required or desired
|  |  | Re-use – re-sanitize | Moderate | Review against guidance | Training supplies guidance
|  |  | Set minimum needed to restart (staff) | Moderate | Quantify 3 month need. | How much is enough - what counts as supply
|  |  | OK to purchase | Low | Monitor - who makes determinaton
|  |  | Priority designation | Moderate | Governor’s proclamation LI Wx Priority | Is it?
|  |  | Group purchase | Moderate | Who would participate and lead
Intake | Staff – Staff – Work space | Moderate | Remote work from home | Moderate | Internet Access Issues | Reimbursement
|  |  | Secure access to systems and tools | varies | Data security VPN for servers
|  |  | Communications | Low to moderate | Office mobiles (or Turnoff Caller ID)
|  |  | Split shifts and space redesign – extra cleaning | Low to moderate | Low to moderate | Scheduling return to work
|  |  | Serological testing | ??? To High | Policy, proceedures testing systems | Availabiltiy Privacy Acc
Intake | Staff – Clients -- Client to Client In person Application - Waiting Rooms | Moderate | Shift to mail – telephone – e-mail | significant could double | Extra protocols and tools - Extra Time | Access issues - who is excluded time to qualify
|  |  | Electronic Signatures | Significant if no systems in place | Upgrades to exising it processes - integration into existing systems. | Policy
|  |  | Dis-infect mail | Low | Dedicate person for scheduling
|  |  | Reduced documentation | Low | Audit risk
|  |  | Drop off - drive by | Low |  | Access issues - who is excluded
Intake | Staff client Notarization Requirements | Low | Suspend for Duration | Low | Policy | Audit risk
Intake | Staff to to staff Access to Paper Records - Files | Low | Conversion to Electronic Storage (PDF – etc) | Could be significant | Technology Conversion past records
|  |  | Conversion to Auto Project Management |  | Forms conversion -- data base management
Intake | Risk Triage - Scheduling | Moderate | Client Risk Assessment – Vulnerability | Low | Develop questions and scripts | HIPPAA
|  |  | Prioritize "low risk" households for start up | Low | Develop criteria - assign priority communicate to client | Coordination with priorites (waiver?) Additional Communication Additional data for internal use. Liability
|  |  | Allow wait list to defer. Communicate risk in intake -- opt out option. | Low to moderate | Protocols and communication | Increased client aquistion costs
Audit - Pre-audit | Multiple Visits - Client to client and staff to client | Moderate to High | Clean protocols -change PPE etc | Moderate | Develop protocols | PPE availabilty - training
|  |  | Reduce number of visits day | Low | What is the right number | Slow pipeline decrease efficiency
|  |  | Eliminate pre - audit or consolidate | Moderate | New protocol - how to handle education | Slow pipeline decrease efficiency -education
|  |  | Require full PPE (respirator) for entireaudit | Moderate | When to suit up - protocols | Interferes with education -- fear factor? What will the neighbors think?
|  |  | Multi-family -- work existing inventory | Low | Review existing inventory | Temporary solution - restart - not an option
|  |  | Remote audits - client drives | Moderate | Protocols - may be dependent of client technology | Data privacy equity issues
|  |  | Remote pre-audits - measure your attic | Low | Protocols - may be dependent of client technology | Whats a verifiable measure (can't see(
|  |  | Serological testing - mmunity certificate | ??? To High | Policy, proceedures testing systems | Availability Privacy Access
Audit - Pre-audit | Diagnostic Testing - Blower Door | Moderate or ?? | Assess risk - is it an increased risk | Low | On line search check with BPI and industry | May not be an increased risk or likely inconclusive
|  |  | Waive testing? In some or all cases | ?? | Protocols | On what basis for which homes?
|  |  | Delay or defer hard to test homes (gas - complex SB) | ?? | Protocols | Record keeping
|  |  | Respirator and PPE while doing testing (and crawls and attics) - cloth mask otherwise | Moderate | Revise audit protocol and structure
|  |  | Temporary relocate clients during testing - disinfect before returning | Low moderate | Protocol | Which surfaces which methods
Audit - Pre-audit | Transportaton - Staff to staff | Low | Separate travel | Low | Agency vehicles -- mileage remimbursement | Use of private vehicles
|  |  | Cloth masks | Very Low | Sufficient to meet guidelines | Can employees refuse
Audit - Pre-audit | Education staff -client | Low Moderate | Facetime and video links | Low Moderate | Tools and protocals -- | Equity and access no leave behind mail
|  |  | Safe signature protocols (sleeve and dispose | Low | Customize
|  |  | Hard copy and print or send links | Low+ | Need to figure out how - whether can communicate | Client face to face missing not all can do
|  |  | Electronic Signatures | Moderate+ | Technology - cleaning protocols for devices
|  |  | Safe distance protocals | Low moderate | Protocols - | Can do with a mask
|  |  | Offer provide cloth masks | Low |  | Hard to train with a mask
Scope and Contract | Confirming Audit with Contractor | Low Moderate | Video - go pro during audit | Moderate | Need protocols -- contractor tools and equipment = scheduling | Translate - Loss of interaction -- video accuracy tricky
|  |  | More change orders | Moderate |  | Allowable
|  |  | Social distance and cloth masks | Low | Protocols - | client interaction issues - contractor buy in
Installation | On site Risk Management | Moderate | On site risk assessment | Low ? | When to conduct - risk classification - add to audit | Yet another tab in the audit workbook
|  |  | COVID check list | Low ? | Develop check list | Required or desired -value added?
|  |  | On site safety plan per Governor Phase 1 | Moderate to high | Standard plan with adjustments protocol | Does it apply - does it need to be posted? How enforced? PPE availability
|  |  | Client education (what to expect from contractors | Low | Training and communications issues | Not clients job - contractor trust
|  |  | Safety plan and protocol monitoring (spot) | Low to moderate | Spot or surprise inspections -- client ed | Trusting contractors
Installation | Material Availability | ?? | Pre order and inventory | Low | Commerce OK - Inventory and tracking system | Risk of have long inventory - matching to projects
|  |  | Priority -- Group Purchase | High | Don't really have mechanism
Installation | Contractor Client Exposures |  | Protocols (in room isolation) | Low |  | Communication enforcement -scheduleing
|  |  | Vulnerable Client - Skipping higher risk measures in interior spots | Moderate | What are higher risk measures | Issues with funding rules - can you skip measures
|  |  | Clean and disinfect after | Low moderate | What to wipe down every day - protocols | Does it make a difference - supplies
|  |  | Contractor Management | ?? | Protocols and tools for coordination schedules | Not clear if this reduces risk? Multiple contractors - hard to social distance? Multiple visits more possible exposures
|  |  | Phasing or splitting work (inside/outside) | ?? | What measures could be done without interior access? | Maybe easier defer or postpone. Record keeping.
|  |  | Contactless work proceedures for outside | Low moderate | Protocols | Client and contractor training called for - additional scheduling
|  |  | Lead safe practices (containment) for high risk clients (or any interior work) | Moderate | Protocols and when to apply | Maybe easier defer or postpone.
|  |  | Duct blaster -- room protection | ?? | When to deploy
|  |  | Client relocation | High | Proceedures | What situations - relocation safe
Quality Assurance | Contractor Staff | Low Moderate | Remote -- Go Pro | Low | Allowable in proceedures | Storage sign off -documentationn
Close out | Documenation and reporting | Low ?? | Cost reporting guidance for additional cost | Low to moderate | Develop guidance - communicate and train | Need to document or at least tell the story of extra health costs. Necessary vs nice to have
| File documentation | ?? | Guidance on any changed requirements? Need for a checklist or other tools | ?? | What is needed beyond existing- checklist helpful or extra work. Required or optional | Who is it for what does it add