## Status
(AGENCY)
Date: 02/02/2017
Version: 1.2
ASSESSMENT = OUTLINE RISK STATUS, IDENTIFICATION, CATEGORIZATION, IMPACT AND PROBABILITY, AND PRIORITIZATION
Quantity | 1 | 2 | 3 | 4
Program administration | 6 | 8 | 1 | 0
Financial grasp and controls | 8 | 1 | 0 | 0
Client outreach | 6 | 3 | 0 | 0
Quality fieldwork | 2 | 2 | 3 | 0
Percentage | 1 | 2 | 3 | 4
Program administration | 40% | 53.33% | 6.667% | 0%
Financial grasp and controls | 88.89% | 11.11% | 0% | 0%
Client outreach | 66.67% | 33.33% | 0% | 0%
Quality fieldwork | 28.57% | 28.57% | 42.86% | 0%

## Identification
RISK
Client re-qualifications
Deficient clear and consistent DOE and CEO Wx messaging from upper management
Deficient AM preparation
Deficient audit through inspection documented workflow process and implementation
Deficient checks, balances, quality control, and quality assurance built into financial processes
Deficient clear and consistent internal messaging from upper management
Deficient DOE and CEO Wx policies and procedures accuracy, access, understanding, and implementation
Deficient DOE and CEO Wx prioritization schemes understanding and implementation
Deficient internal inspection chain documentation and implementation
Deficient internal policies and procedures accuracy, access, understanding, and implementation
Deficient internal record keeping policies and procedures
Deficient management of client expectations
Deficient minimum county allocations understanding and implementation
Deficient planning and expenditure of funds based on priority
Deficient QA preparation
Deficient RFA response misaligned with internal policies and procedures
Deficient SWS compliant measure installations
Deficient targeting and service to utility partner clients
Deficient understanding of best-methods, and how and when to apply them
Deficient unit production and per unit average management plan
Employee turnover, staff vacancies, organizational culture change, and deficient succession planning
Inability to pay-back monthly advances
Inaccurate and disproportionate funding sources and categories spending
Inaccurate and incomplete client file documentation
Inaccurate and insufficient budgeting and understanding
Inaccurate and insufficient category tracking and understanding
Inaccurate and insufficient reporting and understanding
Inaccurate and uninformed audit assessments
Infrequent DOE and CEO Wx policies and procedures review meetings
Infrequent internal policies and procedures review meetings
Insufficient outreach and service
Mixed categories or ambiguous separation
Mixed funding sources or ambiguous separation
No permanent and secure file locations
Over-outreach
Satellite offices
Tardiness with AM report signature page submission and action item implementation
Tardiness with QA report signature page submission and finding, recommendation, and concern implementation
Unaware of or ignoring underserved counties
Utility partner to agency pilot programs

## Categorization
SUCCESS CATEGORY | SUCCESS SUBCATEGORY | RISK
Program administration | Adherence to DOE and CEO Wx policies and procedures | Deficient DOE and CEO Wx policies and procedures accuracy, access, understanding, and implementation
Deficient clear and consistent DOE and CEO Wx messaging from upper management
Infrequent DOE and CEO Wx policies and procedures review meetings
Deficient unit production and per unit average management plan
Employee turnover, staff vacancies, organizational culture change, and deficient succession planning
Satellite offices
| Accurate and traceable record keeping | Deficient internal record keeping policies and procedures
Inaccurate and incomplete client file documentation
No permanent and secure file locations
| Robust internal policies and procedures aligned with RFA response | Deficient internal policies and procedures accuracy, access, understanding, and implementation
Deficient clear and consistent internal messaging from upper management
Infrequent internal policies and procedures review meetings
Deficient RFA response misaligned with internal policies and procedures
| Responsiveness to CEO Wx AM reporting | Deficient AM preparation
Tardiness with AM report signature page submission and action item implementation
Financial grasp and controls | Accurate budgeting, category tracking, and reporting | Inaccurate and insufficient budgeting and understanding
Inaccurate and insufficient category tracking and understanding
Inaccurate and insufficient reporting and understanding
| Clear separation of funding sources and categories | Mixed funding sources or ambiguous separation
Mixed categories or ambiguous separation
| Accurate and proportional spending | Deficient checks, balances, quality control, and quality assurance built into financial processes
Inaccurate and disproportionate funding sources and categories spending
Inability to pay-back monthly advances
| Expenditure of allocated funds based on priority | Deficient planning and expenditure of funds based on priority
Client outreach | Adherence to DOE and CEO Wx prioritization schemes | Deficient DOE and CEO Wx prioritization schemes understanding and implementation
Deficient management of client expectations
| Meet minimum county allocations | Deficient minimum county allocations understanding and implementation
Insufficient outreach and service
Over-outreach
Client re-qualifications
| Focus on underserved counties | Unaware of or ignoring underserved counties
| Target and serve utility partner clients | Deficient targeting and service to utility partner clients
Utility partner to agency pilot programs
Quality fieldwork | Accurate and informed auditing | Deficient audit through inspection documented workflow process and implementation
Inaccurate and uninformed audit assessments
| SWS compliant measure installations | Deficient SWS compliant measure installations
Deficient understanding of best-methods, and how and when to apply them
| Documented and implemented internal inspection chain | Deficient internal inspection chain documentation and implementation
| Responsiveness to CEO Wx QA reporting | Deficient QA preparation
Tardiness with QA report signature page submission and finding, recommendation, and concern implementation

## Impact & Probability
SUCCESS CATEGORY | SUCCESS SUBCATEGORY | RISK | Impact | Probability | Prioritization
Program administration | Adherence to DOE and CEO Wx policies and procedures | Deficient DOE and CEO Wx policies and procedures accuracy, access, understanding, and implementation | 2 | 2 | 2
|  | Deficient clear and consistent DOE and CEO Wx messaging from upper management | 2 | 2 | 2
|  | Infrequent DOE and CEO Wx policies and procedures review meetings | 3 | 1 | 2
|  | Deficient unit production and per unit average management plan | 2 | 1 | 1
|  | Employee turnover, staff vacancies, organizational culture change, and deficient succession planning | 3 | 1 | 2
|  | Satellite offices | 1 | 1 | 1
| Accurate and traceable record keeping | Deficient internal record keeping policies and procedures | 3 | 2 | 3
|  | Inaccurate and incomplete client file documentation | 2 | 2 | 2
|  | No permanent and secure file locations | 1 | 1 | 1
| Robust internal policies and procedures aligned with RFA response | Deficient internal policies and procedures accuracy, access, understanding, and implementation | 2 | 2 | 2
|  | Deficient clear and consistent internal messaging from upper management | 2 | 2 | 2
|  | Infrequent internal policies and procedures review meetings | 3 | 1 | 2
|  | Deficient RFA response misaligned with internal policies and procedures | 2 | 1 | 1
| Responsiveness to CEO Wx AM reporting | Deficient AM preparation | 1 | 1 | 1
|  | Tardiness with AM report signature page submission and action item implementation | 1 | 1 | 1
Financial grasp and controls | Accurate budgeting, category tracking, and reporting | Inaccurate and insufficient budgeting and understanding | 1 | 1 | 1
|  | Inaccurate and insufficient category tracking and understanding | 1 | 1 | 1
|  | Inaccurate and insufficient reporting and understanding | 2 | 2 | 2
| Clear separation of funding sources and categories | Mixed funding sources or ambiguous separation | 1 | 1 | 1
|  | Mixed categories or ambiguous separation | 1 | 1 | 1
| Accurate and proportional spending | Deficient checks, balances, quality control, and quality assurance built into financial processes | 1 | 1 | 1
|  | Inaccurate and disproportionate funding sources and categories spending | 1 | 1 | 1
|  | Inability to pay-back monthly advances | 1 | 1 | 1
| Expenditure of allocated funds based on priority | Deficient planning and expenditure of funds based on priority | 1 | 1 | 1
Client outreach | Adherence to DOE and CEO Wx prioritization schemes | Deficient DOE and CEO Wx prioritization schemes understanding and implementation | 2 | 1 | 1
|  | Deficient management of client expectations | 2 | 2 | 2
| Meet minimum county allocations | Deficient minimum county allocations understanding and implementation | 2 | 2 | 2
|  | Insufficient outreach and service | 2 | 1 | 1
|  | Over-outreach | 1 | 1 | 1
|  | Client re-qualifications | 2 | 1 | 1
| Focus on underserved counties | Unaware of or ignoring underserved counties | 2 | 2 | 2
| Target and serve utility partner clients | Deficient targeting and service to utility partner clients | 2 | 1 | 1
|  | Utility partner to agency pilot programs | 1 | 1 | 1
Quality fieldwork | Accurate and informed auditing | Deficient audit through inspection documented workflow process and implementation | 2 | 2 | 2
|  | Inaccurate and uninformed audit assessments | 3 | 3 | 3
| SWS compliant measure installations | Deficient SWS compliant measure installations | 2 | 2 | 2
|  | Deficient understanding of best-methods, and how and when to apply them | 3 | 3 | 3
| Documented and implemented internal inspection chain | Deficient internal inspection chain documentation and implementation | 3 | 2 | 3
| Responsiveness to CEO Wx QA reporting | Deficient QA preparation | 1 | 1 | 1
|  | Tardiness with QA report signature page submission and finding, recommendation, and concern implementation | 1 | 2 | 1

## Prioritization
SUCCESS CATEGORY | SUCCESS SUBCATEGORY | RISK | Impact | Probability | Prioritization
Quality fieldwork | Accurate and informed auditing | Inaccurate and uninformed audit assessments | 3 | 3 | 3
Quality fieldwork | SWS compliant measure installations | Deficient understanding of best-methods, and how and when to apply them | 3 | 3 | 3
Program administration | Accurate and traceable record keeping | Deficient internal record keeping policies and procedures | 3 | 2 | 3
Quality fieldwork | Documented and implemented internal inspection chain | Deficient internal inspection chain documentation and implementation | 3 | 2 | 3
Program administration | Adherence to DOE and CEO Wx policies and procedures | Deficient DOE and CEO Wx policies and procedures accuracy, access, understanding, and implementation | 2 | 2 | 2
Program administration | Adherence to DOE and CEO Wx policies and procedures | Deficient clear and consistent DOE and CEO Wx messaging from upper management | 2 | 2 | 2
Program administration | Accurate and traceable record keeping | Inaccurate and incomplete client file documentation | 2 | 2 | 2
Program administration | Robust internal policies and procedures aligned with RFA response | Deficient internal policies and procedures accuracy, access, understanding, and implementation | 2 | 2 | 2
Program administration | Robust internal policies and procedures aligned with RFA response | Deficient clear and consistent internal messaging from upper management | 2 | 2 | 2
Financial grasp and controls | Accurate budgeting, category tracking, and reporting | Inaccurate and insufficient reporting and understanding | 2 | 2 | 2
Client outreach | Adherence to DOE and CEO Wx prioritization schemes | Deficient management of client expectations | 2 | 2 | 2
Client outreach | Meet minimum county allocations | Deficient minimum county allocations understanding and implementation | 2 | 2 | 2
Client outreach | Focus on underserved counties | Unaware of or ignoring underserved counties | 2 | 2 | 2
Quality fieldwork | Accurate and informed auditing | Deficient audit through inspection documented workflow process and implementation | 2 | 2 | 2
Quality fieldwork | SWS compliant measure installations | Deficient SWS compliant measure installations | 2 | 2 | 2
Program administration | Adherence to DOE and CEO Wx policies and procedures | Infrequent DOE and CEO Wx policies and procedures review meetings | 3 | 1 | 2
Program administration | Adherence to DOE and CEO Wx policies and procedures | Employee turnover, staff vacancies, organizational culture change, and deficient succession planning | 3 | 1 | 2
Program administration | Robust internal policies and procedures aligned with RFA response | Infrequent internal policies and procedures review meetings | 3 | 1 | 2
Quality fieldwork | Responsiveness to CEO Wx QA reporting | Tardiness with QA report signature page submission and finding, recommendation, and concern implementation | 1 | 2 | 1
Program administration | Adherence to DOE and CEO Wx policies and procedures | Deficient unit production and per unit average management plan | 2 | 1 | 1
Program administration | Robust internal policies and procedures aligned with RFA response | Deficient RFA response misaligned with internal policies and procedures | 2 | 1 | 1
Client outreach | Adherence to DOE and CEO Wx prioritization schemes | Deficient DOE and CEO Wx prioritization schemes understanding and implementation | 2 | 1 | 1
Client outreach | Meet minimum county allocations | Insufficient outreach and service | 2 | 1 | 1
Client outreach | Meet minimum county allocations | Client re-qualifications | 2 | 1 | 1
Client outreach | Target and serve utility partner clients | Deficient targeting and service to utility partner clients | 2 | 1 | 1
Program administration | Adherence to DOE and CEO Wx policies and procedures | Satellite offices | 1 | 1 | 1
Program administration | Accurate and traceable record keeping | No permanent and secure file locations | 1 | 1 | 1
Program administration | Responsiveness to CEO Wx AM reporting | Deficient AM preparation | 1 | 1 | 1
Program administration | Responsiveness to CEO Wx AM reporting | Tardiness with AM report signature page submission and action item implementation | 1 | 1 | 1
Financial grasp and controls | Accurate budgeting, category tracking, and reporting | Inaccurate and insufficient budgeting and understanding | 1 | 1 | 1
Financial grasp and controls | Accurate budgeting, category tracking, and reporting | Inaccurate and insufficient category tracking and understanding | 1 | 1 | 1
Financial grasp and controls | Clear separation of funding sources and categories | Mixed funding sources or ambiguous separation | 1 | 1 | 1
Financial grasp and controls | Clear separation of funding sources and categories | Mixed categories or ambiguous separation | 1 | 1 | 1
Financial grasp and controls | Accurate and proportional spending | Deficient checks, balances, quality control, and quality assurance built into financial processes | 1 | 1 | 1
Financial grasp and controls | Accurate and proportional spending | Inaccurate and disproportionate funding sources and categories spending | 1 | 1 | 1
Financial grasp and controls | Accurate and proportional spending | Inability to pay-back monthly advances | 1 | 1 | 1
Financial grasp and controls | Expenditure of allocated funds based on priority | Deficient planning and expenditure of funds based on priority | 1 | 1 | 1
Client outreach | Meet minimum county allocations | Over-outreach | 1 | 1 | 1
Client outreach | Target and serve utility partner clients | Utility partner to agency pilot programs | 1 | 1 | 1
Quality fieldwork | Responsiveness to CEO Wx QA reporting | Deficient QA preparation | 1 | 1 | 1

## (Prioritization Matrix)
| Low | Medium-Low | Medium-High | High
Low | 1 | 1 | 2 | 3
Medium-Low | 1 | 2 | 3 | 3
Medium-High | 2 | 3 | 3 | 4
High | 3 | 3 | 4 | 4