## Template July 1- 2022 State Pla
Task | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Status / Comments
WAP State Plan Submission
Pre-Planning Updates |  | 2022-11-01 | 2023-02-01
Update Operations and Policy Manuals |  | 2022-11-01 | 2022-11-30
Update T&TA Plans |  | 2022-11-30 | 2022-12-21
Update Monitoring Plans |  | 2022-12-21 | 2023-01-11
Update H&S Plans |  | 2023-01-11 | 2023-02-01
Perform Risk Assessment on Subgrantees |  | 2023-02-01 | 2023-02-11
Hold meeting with Subgrantees for input into State Plan |  | 2023-02-01 | 2023-02-15
Review Carry-over projections |  | 2023-02-01 | 2023-02-08
Pull/Print SAMs and UEI on all Subgrantees |  | 2023-02-01 | 2023-02-11
DOE Release of WPN 23-1
Review WPN 23-1 for updates and additions |  | 2022-12-13 | 2022-12-14
Copy or Create NEW state plan in PAGE |  | 2022-12-14 | 2022-12-14
Begin Edits to State Plan
Mandatory Sections
Complete SF-424 & SF-424A |  | 2023-02-14 | 2023-02-28 |  |  | You may use WPN 22-2 for Budget Planning if WPN 23-2 is not released yet; include language in public hearing notice that when WPN 23-2 is released the budget numbers will be modified.
Budget Justification |  | 2023-02-14 | 2023-02-28
Review and Approval of Budget |  | 2023-03-01 | 2023-03-04 |  |  | Recommend both internal review and DOE review
Provide budget for Subgrantee Contracts |  | 2023-03-07 | 2023-03-07 |  |  | Aim for Subgrantee contract execution to align with award start date of April 1
Annual File |  | 2023-02-21 | 2023-02-25
Master File |  | 2023-02-25 | 2023-03-07
Internal Review and Approval of DRAFT core state plan |  | 2023-03-07 | 2023-03-11 |  |  | The SF-424; SF 424A; Annual File and Master File are required for the public hearing
Notify DOE PO that state plan is ready for PRE-Review |  | 2023-03-11 | 2023-03-11
Required Attachments
Health and Safety Plan |  | 2023-03-14 | 2023-03-31 |  |  | If not included in Master File
T&TA Plan |  | 2023-03-14 | 2023-03-31 |  |  | If not included in Master File
QCI Inspection Form / Tech Monitoring Form |  | 2023-03-14 | 2023-03-31
Public Hearing Transcript & Notice with 10 days |  | 2023-03-14 | 2023-03-31
PAC Activity Documentation and Meeting Minutes |  | 2023-04-01 | 2023-04-06
Indirect Rate Agreement / Cost Allocation Plan |  | 2023-03-14 | 2023-03-31
Single Audit |  | 2023-03-14 | 2023-03-31
SF-Disclose of Lobbying Activities |  | 2023-03-14 | 2023-03-31
Admin / Fiscal Monitoring Instrument |  | 2023-03-14 | 2023-03-31
Budget / Subgrantee Allocations |  | 2023-03-14 | 2023-03-31 |  |  | Sometimes this is an excel file or .pdf
Draft State Plan and Publish for Review
Host PAC Meeting for review of state plan |  | 2023-04-01 | 2023-04-08
Generate presentation for PAC |  | 2023-03-28 | 2023-04-01
PAC Meeting Minutes |  | 2023-04-08 | 2023-04-11 |  |  | This is a required upload
Draft Public Hearing Notice
Publish DRAFT State Plan for Public Hearing |  | 2023-04-01 | 2023-04-01
Public Hearing Notice Approved, Published |  | 2023-04-01 | 2023-04-01
Schedule Public Hearing, min 10 days notice
Draft a formal transcript to read for Public Hearing |  | 2023-04-11 | 2023-04-13
Host Public Hearing |  | 2023-04-13 | 2023-04-13 |  |  | Can be done virtually or in-person
Review Public Hearing Comments |  | 2023-04-13 | 2023-04-15
Formal transcript for hearing |  | 2023-04-13 | 2023-04-15 |  |  | This is a required upload
Submit Plan to DOE |  | 2023-04-19 | 2023-04-20 |  |  | Goal of submitting State Plan 2 weeks before the May 3 deadline.
Confirm all Required Uploads are in PAGE |  | 2023-04-19 | 2023-04-19
Notify DOE PO that plan is submitted |  | 2023-04-20 | 2023-04-20 |  |  | DUE May 3 at 12:00 noon - Best Practice to submit early
State Plan Approval Process
Set up DOE meeting for first review |  | 2023-05-04 | 2023-05-06 |  |  | Recommend setting up a formal meeting with DOE PO to review
Make revisions if needed |  | 2023-05-06 | 2023-05-12
DOE PO Team approval |  | 2023-05-12 | 2023-05-17
DOE CO Review- Golden |  | 2023-05-17 | 2023-05-31
Make revisions if needed |  | 2023-06-01 | 2023-06-08
DOE CO Approval - Golden |  | 2023-06-08 | 2023-06-30
DOE Approval on State Plan |  | 2023-06-08 | 2023-06-30
Accept the award in FedConnect |  | 2023-06-30 | 2023-06-30
Notify Subgrantees and Execute Contracts |  | 2023-07-01 | 2023-07-01 |  |  | Aim to execute Subgrantee Contracts on the Award Start Date