## Action Plan - BLANK
CSBG STATE OFFICE ACTION PLAN
ACTION | WHO? | WHEN? | DEPENDENCY | NOTES / QUESTIONS
A.) CAP PLANS
A1.) Development of Plan Template
A2.) Review & Approval
A3.) Community Needs Assessments |  |  |  | Required every 3 years or more often
B.) CSBG STATE PLAN |  |  |  | Determine if your state uses 1 or 2 year plan
B1.) Development of Plan
B2.) Gather Input
B3.) Hearing
B4.) Approval
B5.) Submission |  | August 30
C.) FUNDING
C1.) Contracts |  |  | A2.) Review & Approval of CAP Plan
C2.) Invoices & Reimbursements |  |  | C1.) Contracts
D.) MONITORING
D1.) Contract/compliance monitoring |  |  |  | Required triennially
D1a.) Risk Assessment
D1b.) Monitoring Tool |  |  | C1.) Contracts
D1c.) Monitoring schedule |  |  | D1a.) Risk Assessment
D1d.) Issuing monitoring reports |  |  |  | Issue monitoring reports within 60 days
D2.) Org standards monitoring |  |  |  | Required annually
D2a.) Monitoring Tool
D2b.) Monitoring schedule
D2c.) Issuing monitoring reports
E.) REPORTING
E1.) CSBG Annual Report
E1a.) Schedule of due dates for reports
E1b.) Gather/input data from agencies
E1c.) Module 1 |  |  | D2.) Org Standards Monitoring
E1d.) Review Data |  |  | E1b.) Gather/input data from agencies
E1e.) Submit Data |  | March 30 | E1d.) Review Data
F.) Training & Technical Assistance
F1.) TTA Plan
F1a.) TTA Schedule
F2.) RPIC
F2a.) TTA Plan
F2b.) Joint activities with Association
G.) ACSI
G1.) Support ACSI Survey Completion |  | Every Other Year
G2.) Set Improvement Targets |  |  |  | Targets in State Plan; Outcomes in Annual Report
G3.) Improvement Activities |  |  |  | Vary depending on agency feedback