## Template July 1- 2024 State Pla
Task | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Status / Comments
WAP State Plan Submission
Pre-Planning Updates |  | 2023-11-01 | 2024-02-01
Update Operations and Policy Manuals |  | 2023-11-01 | 2023-11-30
Update T&TA Plans |  | 2024-11-29 | 2024-12-20
Update Monitoring Plans |  | 2024-12-20 | 2024-01-11
Update H&S Plans |  | 2024-01-11 | 2024-02-01
Pre-Planning Office Prep
Note any staff changes |  | 2023-11-01 | 2023-11-30
Bring new up to date on roles and expectations |  | 2023-11-01 | 2023-12-01
Convene all task owners to review timeline |  | 2023-11-01 | 2023-12-01
Perform Risk Assessment on Subgrantees |  | 2024-02-01 | 2024-02-12
Hold meeting with Subgrantees for input into State Plan |  | 2024-02-01 | 2024-02-15
Review Carry-over projections |  | 2024-02-01 | 2024-02-08
Pull/Print SAMs and UEI on all Subgrantees |  | 2024-02-01 | 2024-02-12
DOE Release of WPN 24-1
Review WPN 24-1 for updates and additions |  | 2024-12-12 | 2024-12-13
Copy or Create NEW state plan in PAGE |  | 2024-12-13 | 2024-12-16
Begin Edits to State Plan
Mandatory Sections
Complete SF-424 & SF-424A |  | 2024-02-14 | 2024-02-28 |  |  | You may use WPN 23-2 for Budget Planning if WPN 24-2 is not released yet; include language in public hearing notice that when WPN 24-2 is released the budget numbers will be modified.
Budget Justification |  | 2024-02-14 | 2024-02-28
Review and Approval of Budget |  | 2024-03-01 | 2024-03-04 |  |  | Recommend both internal review and DOE review
Provide budget for Subgrantee Contracts |  | 2024-03-07 | 2024-03-07 |  |  | Aim for Subgrantee contract execution to align with award start date of April 1
Annual File |  | 2024-02-21 | 2024-02-26
Master File |  | 2024-02-26 | 2024-03-07
Internal Review and Approval of DRAFT core state plan |  | 2024-03-07 | 2024-03-11 |  |  | The SF-424; SF 424A; Annual File and Master File are required for the public hearing
Notify DOE PO that state plan is ready for PRE-Review |  | 2024-03-11 | 2024-03-11
Required Attachments
Health and Safety Plan |  | 2024-03-14 | 2024-04-01 |  |  | If not included in Master File
T&TA Plan |  | 2024-03-14 | 2024-04-01 |  |  | If not included in Master File
QCI Inspection Form / Tech Monitoring Form |  | 2024-03-14 | 2024-04-01
Public Hearing Transcript & Notice with 10 days |  | 2024-03-14 | 2024-04-01
PAC Activity Documentation and Meeting Minutes |  | 2024-04-01 | 2024-04-05
Indirect Rate Agreement / Cost Allocation Plan |  | 2024-03-14 | 2024-04-01
Single Audit |  | 2024-03-14 | 2024-04-01
SF-Disclose of Lobbying Activities |  | 2024-03-14 | 2024-04-01
Admin / Fiscal Monitoring Instrument |  | 2024-03-14 | 2024-04-01
Budget / Subgrantee Allocations |  | 2024-03-14 | 2024-04-01 |  |  | Sometimes this is an excel file or .pdf
Draft State Plan and Publish for Review
Host PAC Meeting for review of state plan |  | 2024-04-01 | 2024-04-08
Generate presentation for PAC |  | 2024-03-28 | 2024-04-01
PAC Meeting Minutes |  | 2024-04-08 | 2024-04-11 |  |  | This is a required upload
Draft Public Hearing Notice
Publish DRAFT State Plan for Public Hearing |  | 2024-04-01 | 2024-04-01
Public Hearing Notice Approved, Published |  | 2024-04-01 | 2024-04-01
Schedule Public Hearing, min 10 days notice
Draft a formal transcript to read for Public Hearing |  | 2024-04-11 | 2024-04-12
Host Public Hearing |  | 2024-04-12 | 2024-04-12 |  |  | Can be done virtually or in-person
Review Public Hearing Comments |  | 2024-04-12 | 2024-04-15
Formal transcript for hearing |  | 2024-04-12 | 2024-04-15 |  |  | This is a required upload
Submit Plan to DOE |  | 2024-04-18 | 2024-04-19 |  |  | Goal of submitting State Plan 2 weeks before the May 3 deadline.
Confirm all Required Uploads are in PAGE |  | 2024-04-19 | 2024-04-19
Notify DOE PO that plan is submitted |  | 2024-04-19 | 2024-04-19 |  |  | Best Practice to submit early - Deadline is usually May 1-3
State Plan Approval Process
Set up DOE meeting for first review |  | 2024-05-03 | 2024-05-06 |  |  | Recommend setting up a formal meeting with DOE PO to review
Make revisions if needed |  | 2024-05-06 | 2024-05-13
DOE PO Team approval |  | 2024-05-13 | 2024-05-17
DOE CO Review- Golden |  | 2024-05-17 | 2024-05-31
Make revisions if needed |  | 2024-05-31 | 2024-06-07
DOE CO Approval - Golden |  | 2024-06-07 | 2024-06-28
DOE Approval on State Plan |  | 2024-06-07 | 2024-06-28
Accept the award in FedConnect |  | 2024-06-28 | 2024-06-28
Notify Subgrantees and Execute Contracts |  | 2024-07-01 | 2024-07-03 |  |  | Aim to execute Subgrantee Contracts on the Award Start Date or within 48 hours