CSBG Community Action Plan and Needs Assessment Tool Kit

State Community Services Office

Division of Housing and Community Development

Department of Workforce Services

The State Community Services Office has assembled the following tool kit and templates in an effort to provide guidance, training, reporting uniformity to the agencies that administer the Community Services Block Grant program.  The toolkit and templates are a work-in-process.  As new ideas and innovative techniques and procedures emerge, the guides and checklists will be modified in an effort to make the needs assessment and community action plan process as efficient and effective as possible.

Table of Contents

Introduction	4

Process	6

PART 1 PLANNING	7

PART 2 DATA COLLECTION	10

1 – Statistical Data	10

2	– Agency Gathered Data	11

A-	Surveys	11

B-	Focus Groups	13

C-	Personal Interviews	14

D-	Forums	16

E-	Related Plans	17

3 – Needs Assessment Instruction Guide	18

PART 3 ANALYSIS OF DATA AND THE NEEDS ASSESSMENT	19

Completing the Data Analysis Tool:	19

PART 4	20

ISSUE PRIORITIZATION	20

Prioritization questions	20

Prioritization tools	20

PART 5	24

COMMUNITY ACTION PLAN	24

PART 6 PUTTING IT ALL TOGETHER	26

Appendix 1 Tally Survey	27

Appendix 2 Organizing Community Forums	28

Appendix 3 Conducting Focus Groups	33

Appendix 4 Root Cause Analysis	36

Appendix 5 But Why Technique	38

Appendix 6 Outcomes and Outputs	40

# Introduction

The Community Needs Assessment (CNA) is a comprehensive process to determine the needs and resources within a community, to identify barriers and gaps in services, and to identify the partners, tools and assets available within the service area to lift individuals and families out of poverty and encourage self-reliance. The CNA is a key resource for planning, application, program implementation, and evaluation as programs become strategies for addressing identified need via a specific and targeted action plan.  The flexible nature of Community Service Block Grant (CSBG) funding creates a unique opportunity of Community Action Agencies (CAAs) to be able to fill identified gaps identified in the assessment.

Additionally, the CNA is involved with 13 of the CSBG organizational standards:

•	Standard 1.1 – The organization demonstrates low-income individuals’ participation in its activities.

•	Standard 1.2 – The organization analyzes information collected directly from low-income individuals as part of the community assessment.

•	Standard 1.3 – The organization has a systematic approach for collecting, analyzing, and reporting customer satisfaction data to the governing board.

•	Standard 2.2 – The organization utilizes information gathered from key sectors of the community in assessing needs and resources, during the community assessment process or other times. These sectors would include at minimum: community-based organizations, faith- based organizations, private sector, public sector, and educational institutions.

•	Standard 3.1 – The organization conducted a community assessment and issued a report within the past 3 years.

•	Standard 3.2 – As a part of the community assessment, the organization collects and includes current data specific to poverty and its prevalence related to gender, age, and race/ethnicity for their service area(s).

•	Standard 3.3 – The organization collects and analyzes both qualitative and quantitative data on its geographic services area(s) in the community assessment.

•	Standard 3.4 – The community assessment includes key findings on the causes and conditions of poverty and the needs of communities assessed.

•	Standard 3.5 – The governing board formally accepts the completed community assessment.

•	Standard 4.2 – The organization’s Community Action plan is outcome-based, anti-poverty focused, and ties directly to the community assessment.

•	Standard 4.3 – The organization’s Community Action plan and strategic plan document the continuous use of the full ROMA cycle or comparable system. In addition, the organization documents having used the services of a ROMA-certified trainer (or equivalent) to assist in implementation.

•	Standard 6.4 – Customer satisfaction data and customer input, collected as a part of the community assessment, is included in the strategic planning process.

•	Standard 9.1 – the organization has a system or systems in place to track and report client demographics and services customers receive

The CNA is a key component of the annual CSBG application process. It is an essential guideline for matching programs to community need as well as for identifying needed partnerships for unfilled gaps. The CNA and the Community Action Plan (CAP) are part of the State Community Service Office’s (SCSO) assessment of each agency during monitoring and the application review. The CAP provides each agency and the SCSO with a clear link between identified needs and agency goals and program achievement. The CNAs and CAPs are evaluated as follows:

| 1. At risk | There is little or no needs assessment data, and the agency has no system for synthesizing available data to guide the direction of comprehensive agency strategic or operational plans. |
| --- | --- |
| 2. Insufficient but making progress | There are needs assessments for specific programs required by funding sources. The data are only used to meet program requirements |
| 3. Sufficient | Systems exist for utilizing the program needs assessment data on an agency level or for disseminating funding within the agency. There is a regularly conducted, broad based community needs assessment and a system is in place to utilize the data across program lines |
| 4. Sufficient and making strides toward excellence | There is a regularly conducted, broad based community needs assessment and a system is in place to utilize data in developing the agency strategic plan and in formulating goals and objectives |
| 5. Excellent | The agency meets the criteria in 4 and the information from the needs assessment is used in formulating agency goals and objectives in which the board members were involved and they approved. Information is also shared with the community, local policy makers and legislators. The agency needs assessment and strategic plan are utilized in seeking funding through government and private funding sources. |

CNAs can and should be more than just a gathering and an analysis of data. They can also be a basis for creating change. A community based needs assessment can help an agency address poverty by providing a snapshot of poverty in the service area. Agencies can begin to create change by setting a framework for programs and plans that work toward ending poverty or at least stabilizing families and individuals and promoting movement to self-sufficiency. It can provide important community information as to who may be working on issues and where gaps in community services exist. It provides an opportunity to make and develop partnerships. Finally a community needs assessment helps the agency in strategic planning process by providing the foundation for strategic operational planning. The work of the needs assessment requires the agency to evaluate if the agency is meeting the needs of the community and determine what programs or projects may have become obsolete and what programs or projects may provide new opportunities for the agency.

As the Community Action Network, it is essential to our role to provide partners, other providers, and state and local governments completed and comprehensive needs assessments and aid in our local and state efforts to reduce poverty.

# Process

There are multitudes of ways to conduct a needs assessments but the collection of all the information is meaningless unless it is framed within the agency’s mission and vision.  This tool kit was designed to provide support and guidance to agencies conducting needs assessments and Community Action Plans.

#### Federal Requirements for Needs Assessments

In 2001, the U.S. Department of Health and Human Services (“HHS”) issued Information Memorandum 49, requiring eligible entities to conduct needs assessments and use the results to design programs to meet community needs. In 2015, HHS issued Information Memorandum No. 138 establishing Community Services Block Grant (CSBG) Organizational Standards requiring CAAs to conduct a Community Needs Assessment and develop a Community Action Plan to address the needs identified in the needs assessment. As noted above, reference to the CNA is found in 13 of the organizational standards.

#### Six Steps to Develop a Community Needs Assessment

This guide is divided into five areas:

- Planning the CNA

- Data Collection

- Analysis of  Data

- Prioritization of Data and Issues

- Creating the Community Action Plan

- Submission of product

#### End Product

Each agency will submit electronically to SCSO the completed needs assessment tool provided by SCSO. The tool includes templates for:

- Needs Assessment –including Issue Areas Tool with data entered

- Data Analysis

- Prioritization

- Community Action Plan

# PART 1 PLANNING

The following steps are provided as a suggested guide for completing the needs assessment process.

- Create a plan and timeline

- Community Needs assessment requires board approval prior to submission

  - When will the CNA be presented to the board?

  - When will drafts need to be reviewed and prepared for presentation to the board?

- Are other organizations in the community undertaking a needs assessment?

  - Is there possibility a coordination?

  - Could forums be jointly hosted?

  - Do other organizations have data that they are able to share?

- Who will lead the creation of the CNA?

- How much time will be needed for gathering data, conducting forums, administering surveys, interviewing, evaluating and analyzing data, prioritizing issues, and drafting the plan? Generally, many months are required and a +12 month timeline is not uncommon.

- Create a Community Needs Assessment Workgroup

- Organize a committee to develop and oversee an action plan to conduct the needs assessment

- Include diverse members such as management, staff, board members, representatives from partner organizations, and volunteers

- Define the responsibilities of the committee:

Sample responsibilities:

  - Determine what information to collect

  - Determine how to collect the information

  - Determine who will participate in surveys, forums, focus groups & interviews

  - Determine timeline to conduct assessment

  - Develop plan to recruit partners and volunteers to assist in the process

  - Provide oversight and feedback throughout the assessment process

  - Monitor process and ensure completion of needs assessment

- Involve the Board

- Inform the board of need to conduct a community needs assessment

- Solicit board volunteers to serve on community needs assessment workgroup

- Ensure board members participate in the planning meetings

- Ensure the board provides input on the scope of process and information to be collected

- Interview board members

- Define Assessment Goals – What data is needed?

- Identify the goals of the needs assessment.  Clearly define what you expect to know once the assessment is complete in order to determine what data to collect.

Sample Goals are:

  - Identify the causes and conditions of poverty in the CAA’s service area (Required by Organizational Standard 3.4)

  - Determine the level, sources, and demographics of poverty in the CAA’s service area

  - Determine the needs, unmet needs in the CAA’s service area

  - Determine service gaps  and barriers to exiting poverty for low-income persons in agency’s service area

  - Identify community strengths and assets

  - Solicit recommendations of solutions to address barriers and service gaps

  - Review and revise agency programs to support identified needs

- Determine how to collect information

- Issue area tool includes data sources for each quantitative data item. CAA is welcome to go beyond these data points and sources.

- What qualitative data will your CAA collect and how will it collect data in each county served (e.g. surveys, interviews, forums, and focus groups)

- Determine how records related to assessment will be retained

- Develop a task list with staff and volunteer responsibilities

- Develop list of tasks to be accomplished by staff and volunteers or partners

- Assign tasks

- Develop timeline for task completion

- Recruit volunteers and partners

- Identify and contact partner organizations and volunteers

- Identify partners who may be engaged in similar community research

- Determine what part of the needs assessment they can assist with

- Provide timeline to staff and volunteers and partners

Potential Partners and Volunteers

- Members of your agency’s board

- University students in graduate programs (e.g. planning, social work and public affairs)

- Nonprofit partners

- City or county staff in community development departments

- Head Start parents

- School teachers and administrators

- Parent Teacher Associations

- VISTA volunteers

- Chambers of Commerce

- Lions Club

- Churches

- Salvation Army and Religious Charity Organizations

- Present Community Needs Assessment Plan to Board

- Develop a report to present to the board outlining the goals of the CNA, major tasks of the project, the methods that will be used to collect data in each county, and the plan to solicit help from partners and volunteers.

- Present CNA plan to board for approval

- Board should have opportunity to discuss, review community action plan  (and strategic plan) and understand the benchmarks to be reached annually so that progress can be measured and evaluated.

- Assign Tasks and Monitor Progress

- Management meets with staff to make assignments

- Monitor staff progress in completing tasks by deadline in timeline

- Share Results with the Community

- Suggested that agency posts to website

- Share with community partners

# PART 2 DATA COLLECTION

It is important to note that when conducting focus groups and or surveys, agencies must include outreach to members of the communities, populations, and counties they serve, as well as to their current clients, prospective clients, and other service providers or partners who work with the same population that are covered by this assessment.

It is important that each agency understands that each of the areas in the CNA needs to be filled out in entirety. Data sources are listed for all listed data points.

## 1 – Statistical Data

The Issue area tool has been revised to list specific sources for quantitative data. CAAs are expected to gather all data points listed for all counties within the CAA’s service area.  CAA’s are welcome to go beyond the data points listed and to use additional sources.

Other Suggested Data Resources:

American Community Survey (ACS): https://www.census.gov/programs-surveys/acs/

Centers for Disease Control and Prevention:  Drug Overdose Death Rates

https://www.cdc.gov/drugoverdose/data/statedeaths.html

https://www.cdc.gov/drugoverdose/data/statedeaths/drug-overdose-death-2017.html

Community Action Partnership Needs Assessment Tool:

https://communityactionpartnership.com/online_tools/community-needs-assessment-tool/

Community Action Partnership of Utah, Resource Library:

https://caputah.sharepoint.com/sites/CAPUtahResourceLibrary.

MIT Living Wage Calculator:   https://livingwage.mit.edu/

Utah Department of Workforce Services:

Annual Report on Homelessness https://jobs.utah.gov/housing/index.html

Statewide Affordable Housing Assessment  https://jobs.utah.gov/housing/reports/

Annual report on Intergenerational Poverty

https://jobs.utah.gov/edo/intergenerational/

Data Dashboard  https://jobs.utah.gov/wi/data/library/index.html

Utahns Against Hunger: Data and Reports:

https://uah.org/fight-hunger/learn-more/item/67-data-reports

## – Agency Gathered Data

### Surveys

Surveys can be used to explain the statistics that are gathered in each section (e.g. unemployment rose from 4% to 7%, survey data should provide a reasonable explanation of why this occurred). An agency should survey clients, partners, community leaders, vendors and other service providers. Agencies should also gather input (survey or other) from key sectors in the community, including (at minimum): community-based organizations, faith-based organizations, private sector, public sector, and educational institutions. (Required by OS 2.2)

The following steps are recommended for preparing and conducting surveys:

Use surveys to capture specific information from a large number of individuals in a short period of time.

- Design survey forms

- Identify the questions you want the data to answer and what you want to have learned as a result of conducting the survey.

- Design the survey – guide available at Community Tool Box:

https://ctb.ku.edu/en/table-of-contents/assessment/assessing-community-needs-and-resources/conduct-surveys/main

- Identify the people that you will survey

- Determine who you will survey, for example: low income residents in identified census tracts or zip codes with high poverty areas, students in community colleges, staff, volunteers and clients.

- Determine the number of people you will survey

- Determine the number of community residents to survey in each county by using a sample size calculator that determines a sample size for a given confidence level and margin of error and population.  We recommend using a 5% margin of error, and a confidence level of 90%:

Sample Size Calculator http://www.raosoft.com/samplesize.html

- Determine how you will survey

- Determine how you will survey participants: by phone, a mailed form, in person, or by internet ( ie. Survey Monkey http //www.surveymonkey.com)

- The return rate may be small; therefore, utilizing the mail as your only means of gathering the survey information is not recommended.

- Determine when and where to conduct the survey

- Determine a time period for conducting the survey

- Determine the places where the survey will be completed

- Have surveys available at all intake locations or partners’ sites

Sample Places to conduct community surveys:

- Neighborhood Council Meetings

- Head Start Parent Meetings

- Parent Teacher Association Meetings

- Community Meetings

- Nonprofit Organizations Serving Low-Income Persons

- Door to Door

- Persons Attending CAA Forums

- Conduct surveys

- Train staff and volunteers who will conduct surveys

- Distribute survey forms

- Send out invitations for online surveys and reminders to complete it as the deadline approaches

- Tally results of surveys

- Tally results

- Clean data for entry errors

- Refer to Appendix 1 - How To Tally Results of Surveys

- Summarize findings

- Summarize findings and identify the top 5 needs

Considerations

- One should consider having the document translated into the native languages of the agency’s clients if the agency serves a large population on non-English speakers.

- When determining a time limit for surveys, think through when or what may affect the number of clients you might see – what times of the month do clients come in with certain needs (energy assistance, Head Start sign-up, etc.)

- If using mail, consider the costs as you should include a self-addressed stamped envelope for replies (as well as with those left directly at clients homes).

- Think about asking a client the questions versus asking them to fill out a questionnaire for example while they are waiting for services. This will entail training of the staff to ensure the questions are being asked in the same manner as well as providing for an area to ensure confidentiality.

- Do not assume your clients are without access to the internet and computers. A kiosk type computer in the waiting room as well as maintaining internet e-mail addresses on clients can help to capture information in a quick and concise manner.

- For surveying your partners, service providers, and community leaders, begin by compiling a listing of those who you want to contact.

- Analysis of both of these surveys will not only provide information on what clients need from their own viewpoint, but will also provide a picture of how the partners, leaders, and others in the community perceive need - which may not always be the same.

- Keep in mind Organizational Standard 2.2 when tracking qualitative information:

“The organization utilizes information from key sectors of the community in assessing needs and resources, during the community assessment process and at other times. These sectors would include at minimum: community-based organizations, faith-based organizations, private sector, public sector, and educational institutions.”

### Focus Groups

Use focus groups to bring together a broad cross section of low-income individuals and community partners and service providers. Arrange the focus groups for maximum openness and encouragement of participation. Always remember the perceived and real power structures in the community arena including the relations between clients and staff. Multiple focus groups are common and recommended.

The following steps are recommended for preparing and conducting focus groups:

- Design focus groups forms

- Determine what information you want to gather from the focus group and then develop the questions to gather the information you are seeking (for example—a forum may produce insights to previously unidentified barriers...)

- Design the focus group forms by using or modifying Appendix 3: Guidance For Conducting a Focus Group

- Refer to Appendix 2:  Organize a Community Forum for information on forums.

- Identify the people that will be invited to participate in the focus groups

- Develop a list of 15-20 persons to invite to participate in each focus group in each county  and make every effort to have at least 10 of the invitees participate in the focus group

- Determine cities and counties in which to hold focus groups

- Invite persons by telephone and follow-up with a phone call the day prior to event

- Note attendance of representatives from the five sectors (public, private, education, community-based groups, and faith-based groups)—and their participation so as to demonstrate compliance with Organizational Standards.

Sample Persons to invite include:

- Board members

- Public officials

- Representatives from partner organizations

- Neighborhood council leaders

- Community advocates and leaders

- Business and civic leaders

- Educators and school administrators

- Clients

- Religious organizations that serve the needs of low-income persons

- Persons or organizations that the sub-recipient or board identify

- Determine format/venues for the event

- Reserve a meeting facility for each of the planned focus groups

- Hire a professional group facilitator or assign volunteer or staff to role

- Develop an agenda

- Identify the process to hold the meeting and to document input

- Plan to document input at the meeting using a flip chart and to post sheets on walls for attendees to view

- Conduct focus groups

- Provide a list of the top five needs which have been identified in the community surveys and delve more in-depth into the underlying causes, needs, and barriers.

- Summarize information collected

- Review responses from focus groups

- Develop summary

- Sample focus Group Questions

- What would our community look like without poverty?

- What keeps families in poverty?

- What should we as a community do to address poverty?

- How do you define poverty?

- The look of poverty in your county is...

- What does debt look like in our community….(types, amount, etc)

- What can our agency/partners do to support the community to achieve the outcomes to eliminate poverty in your county?

- What are the causes of poverty in our community?

- Identify programs, strategies and initiatives that have been successful in reducing poverty.

- What steps could be taken to reduce poverty in our community?

- What role(s) could our agency/others interested in reducing poverty and creating an economy that works for all-- play in our community?

- What strategies/services do you recognize as successful for moving community members out of poverty?

### Personal Interviews

A final way to gather viewpoints of a community is to conduct personal interviews with the clients, partners, staff, and community leaders. Personal interviews allow you to delve deeper into various aspects of the questions; however, the process of personal interviews will take more time.

The following steps are recommended for preparing and conducting Interviews:

- Design interview forms

- Determine what information you want to gather from interviewees and then develop the questions to gather the information you are seeking

Sample information to gather:

- Thoughts regarding needs in the community

- Thoughts on causes and conditions of poverty in the community

- Community Assets

- Barriers

- Gaps in services

- Opportunities for collaboration

- Recommendations to address needs and barriers

- Identify the people that you will interview

Sample persons to interview:

- Elected officials, both city and county

- Community leaders from civic organizations

- Heads of non-profit organizations serving low-income persons

- Clergy from churches with ministries that serve low-income persons

- Key stakeholders

- Funders

- Neighborhood association or council leaders

- University researchers

- Determine methods to conduct interviews

- Conducting interview in person (preferred)

- Mailing interview form – follow-up to ensure receipt, completion, and return (self-addressed, stamped envelope recommended)

- E-mailing interview form - follow-up to ensure receipt, completion, and return

- Determine when and where to conduct interview

- Offer as many options as possible for opportunities for interviewee to participate

- Pick a place that will make the interviewee feel at ease

- Conduct interviews

- Train staff and volunteers who will conduct surveys

- While conducting interviews, discuss confidentiality and purpose of the interview

- Summarize interviews

- Review responses from interviews and develop summary of input

- Sample questions for partnership or stakeholder focus groups or personal interviews could include the following:

- Do you address this issue or need in the community? (Education, housing, employment, child care, etc.)

- How do you address this issue? (advocacy, direct service, referral)

- What do you see are the challenges facing this issue in the community?

- Who else is working on this issue in your area?

- How would you know your programs were successful?

- Internal focused questions: The CNA, if comprehensive and multi-faceted, should provide the background for a significant portion of the agency’s strategic plan and provide the framework for discovering other programs and funding. The above questions can be revised for such a group and might look like the following

- How do we address this issue or need in the community?

- What do you see are the challenges facing these issues in the community?

- Who do you partner with when you need to help someone who is facing this issue? Who should the agency partner with when addressing these issues?

- How will we know if we are successful?

### Forums

The following steps are recommended for preparing and conducting Forums:

- Design forum forms

- Determine what information you want to gather from in the forums and then develop the questions to gather the information you are seeking.  Design the forum forms by using or modifying Appendix 2 Organize a Community Forum

- Develop an agenda

- Define forum format and venue for event

- Hire a professional group facilitator or assign volunteer or staff to role

- Identify the process to hold the meeting and to document input

- Plan to document input at the meeting using a flip chart and to post sheets on walls for attendees to view

- Determine cities and counties in which to hold forums

- Reserve a meeting facility

- Consider conducting it in conjunction with other community meetings, such as a PTA meeting or a church group meeting

- Determine methods to publicize the forum

Sample methods:

- Newspapers, radio, website, e-mails, phone

- Requesting board members to publicize to elected officials and organizations

- Asking partner organizations to publicize by distributing fliers

- Notifying neighborhood council leaders, community advocates and other leaders

- Notifying business and civic leaders

- Notifying clients at centers

- Asking schools if they might distribute the survey to parents

- Sending invitations to religious organizations that serve the needs of low-income persons and to other persons or organizations that the sub-recipient or board identify

- Conduct forums

- Explain the purpose of the forum

- Solicit input on the top five needs of low-income persons in the community

- Identify barriers that make the need difficult for persons to overcome

- Solicit recommendations for improvements to agency programs

- Summarize information collected

- Review responses from forums and develop summary

### Related Plans

Many communities have already undertaken a number of assessments and generated plans addressing identified needs, challenges, barriers, and gaps. These plans provide a wealth of knowledge for the agency and can inform the agency of what other programs are active in the region. While the service area of other agencies may differ, the plans produced may at least partially inform the CAA.

## 3 – Needs Assessment Instruction Guide

The following sections correspond directly with the layout of the CNA template. Use these next pages as a direct guide on how to fill out those corresponding sections. Each source used to gather data should be representative of individuals AND families that are at or below the 125% poverty level. Sources are provided in the template and the data points that follow each source may be found in the source identified above the data point.

#### Section A – ISSUE Area Characteristics

In this section, sources are provided in the template and the data points that follow each source may be found in the source identified above the data point.  Please complete and provide data for each of the data points for each of the counties within your CAA’s service area. CAAs are welcome to provide additional data points. Should your agency elect to do so, please provide source.

As you collect these area characteristics, use your previous needs assessment (year) or the previous fiscal year as a base year. In the analysis section, you will look for major changes in the numbers you gather with those from the base year.

#### Section B – Summary of Surveys, Focus Groups, Interviews, and Informal Questioning Results

List here your top results from your surveys, community meetings/forums, focus groups, and interviews. The data gathered from these methods should include insight into the Causes of Poverty, Gaps in Services, Barriers to Exiting Poverty, and Individual and Community Needs for the service area.

There are five columns to fill in for each row:

- Column (1) is the subject area (i.e. cause of poverty, gap, barrier, need);

- Column (2) is the Population from which the data was collected(e.g. qualifying CSBG populations);

- Column (3) is the Data Source (e.g. interview with service provider, focus group with clients, survey of youth, questionnaire to clients going through intake, etc.);

- Column (4) is the County that the data was gathered from;

- Column (5) is where you describe the results and provide a description. Results should quantify responses. See the examples in red font in the needs assessment.

# PART 3 ANALYSIS OF DATA AND THE NEEDS ASSESSMENT

Who should be involved in the strategic thinking relative to the analysis?

A cross functional team representing different programs and different levels within the agency and board members can lay the foundation as the agency moves from the needs assessment to the Community Action Plan, and the development of programs and activities. In addition, partners and stakeholders in the community can be a part of the analysis of the data and information. While they may not be involved in the decision making regarding the planning of action steps and implementation, they can offer insight to data and information due to their different perspectives.

#### SUGGESTED PARTICIPANTS

- Agency staff (frontline, middle management and upper management)

- Member(s) of the Board of Directors

- Member(s) of other advisory and related internal boards

- Community stakeholders (service providers, local government program directors, linkages, partners)

Participants should receive the data prior to any discussion. Discussions with partners are meant to reveal patterns in the data and foster discussion.

## Completing the Data Analysis Tool:

The first page asks for an executive summary of the analysis (1-2 pages). Prompts are included to help guide the narrative.

The following pages are the data analysis work sheets. There are series of questions that will be answered for each issue through review of both the quantitative and qualitative data. CAAs are welcome to go beyond these questions and more robustly analyze the data gathered. These questions are provided as a floor for analysis expected of the data gathered.

As the data is reviewed and analyzed, make note of what the data indicate about the causes and conditions of poverty in the service area.

# PART 4

# ISSUE PRIORITIZATION

In this section, be sure to include a detailed description of how the analyzed issues were prioritized in the summary. What factors were considered and why? If any issues were not considered for prioritization, why weren’t they? What community and partners were considered in this process? Who was involved in the process? What factors increased prioritization for the CAA?

The prioritization tool identifies the top issues your agency will address in its Community Action Plan. (CAP) CAP.

### Prioritization questions

One way to begin the process is to hold a general conversation around the gaps, needs, causes, and barriers in each issue area. It is recommended that you document these conversations and meetings.

The following questions are offered to help guide you through the prioritization process:

- What has been done in the past at our agency or another to address this issue?

- Why should we be interested in this issue?

- What can be done to address this issue?

- Who (what agency, group, organization) should address this issue? Can the agency address the issue alone? Who should partner with the agency to address the issue? Who in the agency should address the issue?

- Do we have control over this issue? Do we have control over an aspect of this issue? Control does not mean dominance. In this context it means the agency can actually affect change regarding the issue. For instance – can the agency create the jobs in the community, or can it train the potential employees for jobs that are created by others?

- Do we have the capabilities (skills, funding, and knowledge) to address this issue? Do we have to spend time and resources learning new skills or programs to help address the issue?

- What programs do we currently have that can help address this issue?

- What might we change in our way of doing business that could help address the issue?

- If this is an important issue and we do not have the capabilities to address the issue, who can we partner with to help create the change and address the issue? Is DWS an appropriate referral?

### Prioritization tools

There are various tools that can be used to help in the process of prioritizing issues. Prioritization tools help in reducing the large listing of issues into manageable numbers.

#### Nominal Group process

One of the first ways to begin narrowing down the multiple lists of issues is to use a nominal group process. The most common way this is done is to put on a large paper all of the issues and give the individuals in the group a certain number of sticky notes/dots/or markers and let them ‘vote’ with those dots the issues of their highest priority. Individuals may place one dot/marker on each concern or they may place all their dots on one area if they believe it is the one that is of highest priority. Counting up the dots then provides a reduced list of issues to further refine.

#### Paired comparison technique

By using a paired comparison technique, the team can decide which issue(s) are priorities. In addition, it may help in determining which issue(s) or program(s) to consider reducing or eliminating. It directly compares one issue to another and allows for the group to decide between two equally important issues.

Process: Set up a matrix identifying all the issue areas you have ranked as most important. You will only compare each set of issues once. Through your group discussions you may have determined sub parts of the broader issue categories that need addressing rather than the whole category. For instance, perhaps the graduation rates in the area are adequate; however there is a need for more pre-school services. The example below is utilizing the major categories; however, you should substitute other more defined issue areas that resulted from your discussions.

|  | Use of Income | Education | Employment | Housing | Nutrition | Health | Transportation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Use of Income |  |  |  |  |  |  |  |
| Education |  |  |  |  |  |  |  |
| Employment |  |  |  |  |  |  |  |
| Housing |  |  |  |  |  |  |  |
| Nutrition |  |  |  |  |  |  |  |
| Health |  |  |  |  |  |  |  |
| Transportation |  |  |  |  |  |  |  |

Using information gained through your discussions of the issues, and thinking about whether addressing the issue will either end poverty or stabilize families the individuals in the group will choose one issue as a priority over the other. The group facilitator reads each possible pair and individuals vote on which is the preferred choice to address first.

Example of Comparison Choices

| Comparison | Preferred Choice |
| --- | --- |
| Employment/Education | Employment |
| Employment/Housing | Housing |
| Employment/Nutrition | Employment |
| Employment/Use of Income | Use of Income |
| Employment/Transportation | Employment |
| Employment/Health | Health |
| Education/Housing | Housing |
| Education/Nutrition | Education |
| Education/Use of Income | Use of Income |
| Education/Transportation | Education |
| Education/Health | Health |
| Housing/Nutrition | Nutrition |
| Housing/Use of Income | Housing |
| Housing/Transportation | Housing |
| Housing/Health | Housing |
| Nutrition/Use of Income | Nutrition |
| Nutrition/Transportation | Nutrition |
| Nutrition/Health | Health |
| Use of Income/Transportation | Use of Income |
| Use of Income/Health | Health |
| Transportation/Health | Health |

After all the issues are compared one-to-one, they are scored as to how many times an issue was chosen.

Example Scoring:

| Issue Area | Times Chosen | Total |
| --- | --- | --- |
| Use of Income | XXX | 3 |
| Education | XX | 2 |
| Employment | XXX | 3 |
| Housing | XXXXX | 5 |
| Nutrition | XXX | 3 |
| Health | XXXXX | 5 |
| Transportation |  | 0 |

All ties go through the process again to come up with the prioritized issues. In this case, the new matrix would compare health, housing, employment, nutrition, and use of income. If another tie results, you would then repeat the process until a final prioritization results with no ties.

#### Interrelationship Diagram

A third way to help determine what issue to prioritize is to examine the interrelationships between the core causes of poverty. It helps you to see how addressing one issue may affect another issue.

Process: Begin by listing the top 5 or 6 issues in a circle on a piece of paper. Starting with the first issue, ask whether addressing it will affect the next issue, the third issue, etc. If it will affect the issue, draw an arrow to the issue. If addressing the second issue however will affect the first, draw an arrow from #2 to #1.

Unemployment

Affordable Housing

Lack of available jobs

High Utility Bills

Poor Health

Poor Nutrition

The issue having the most arrows going outward will have the most effect on the others and would therefore be the one to consider as a top priority. When conducting this exercise you may place up there the barriers, gaps, needs, or causes of poverty that the clients referenced the most. Or you may place up there issue area characteristics that are the most alarming. Doing this exercise will also feed into the linkages and partnerships that you need to create or the resources that are most helpful.

Determining Final Priorities

The final priorities are actually a balance between looking at the various results of the tools, discussing the issues as they relate to the agency’s mission and vision, and looking at funding, knowledge and untapped resources. However your agency arrived at its finally determined, prioritized issues, make sure that process is fully explained in the executive summary of the tool.

# PART 5

# COMMUNITY ACTION PLAN

The Community Action Plan is the keystone of this whole process. This is the document that should guide your programmatic decisions and your goals. This document will be used by SCSO in monitoring and as part of the application. You will use your data, analysis, and prioritization documents to create this plan.

You will need to prepare the following subjects and items before you engage in the creation of your Community Action Plan:

- Organizational/Department and or Program Mission Statement

- Organizational/Department and or Program Vision Statement

- All of the prioritized Service Needs, Service Gaps, Barriers to Exiting Poverty, Causes of Poverty, and Issue Areas that you determined and identified in the analysis and prioritization of issues.

- List of the prioritized linkages. These linkages don’t have to align with the prioritized Gaps, Needs, Barriers, and issues areas; however, it is common that most of them will. As you  prepare, make sure you have developed a plan and goals regarding how and when these linkages will be created and what the outcomes will be.

- List of the prioritized partnerships that you will create this next year. As you are preparing these make sure you have developed a plan and goals regarding how and when these partnerships will be created and what the outcomes of the partnerships will be.

- Incorporating ROMA into the report

  - Organizational Standard 4.3 requires the use of a ROMA trainer or implementer to facilitate the development and implementation of the Community Action Plan and Strategic Plan.

  - Organize identified needs using a ROMA Organizing Framework.

  - Complete the Identified Needs column of the table and categorize the identified needs under one of the six National Goal categories.

  - Identify the current services and activities that address the needs and begin to identify what future services may be needed.

  - You will be provided a ROMA chart in the template, In this chart you will describe the Service Needs, Service Gaps, Barriers to Exiting Poverty, Causes of Poverty, and Issue Areas that you determined in ‘Part 4 Prioritization’ with the 3 national goals in the ROMA Process.

- Complete the Logic Model. This is your agency’s measurable plan. Create goals that not only address the prioritized barriers, gaps, causes, needs, and issue areas, but that also help your agency obtain the identified partners and linkages.

  - These goals must have outcomes(measurable progress toward self-sufficiency)

  - These goals must have outputs(activities that you will engage in)

  - These goals must meet the SMART criteria (specific, measurable, attainable, relevant, and timely)

See Appendix 6 on criteria for outputs, outcomes, and SMART goals.

# PART 6 PUTTING IT ALL TOGETHER

At this point the CAP, the Prioritization, Data Analysis, and the Issue Area tool should all be complete.

Please submit each as a separate attachment on an email. Also include minutes (may be draft) reflecting board approval of the needs assessment and Community Action Plan. , SCSO requests that it be organized in the following order:

- Community Action Plan

- Prioritization Tool

- Data Analysis Tool

- Issue Area Tool

- Sample of supporting documentation

  - Please submit sample documentation from survey, interview, focus groups results; relevant meeting minutes, etc

- Board approval of the CAP and the Needs Assessment as required by Standard 3.5.

  - Board Minutes, or other written approval (may be a note from board chair noting the date of approval of needs assessment and plan).

- Compliance documentation for Standard 4.3—ROMA Implementer or Trainer assisted in implementation of community action plan and strategic plan, and that both documents reflect continuous use of full ROMA cycle.

Complete submission (including back-up documentation) will facilitate SCSO with desk top review of compliance with related organizational standards.

# Appendix 1 Tally Survey

Once the surveys have been completed, develop an Excel spreadsheet or use a survey form to record the ratings given by survey respondents to each question.

Once you have recorded how many persons rated each question, then you will mathematically calculate the value to assign to each question.  In the example below, each question has five possible responses, and each response has a number/score assigned to it.  The number/score, 0 thru 4, is the weight/value that will be given to each response.

An example of how to calculate responses to surveys:

|  | NEEDS | Don’t Know (0) | Not Needed (1) | Rarely Needed (2) | Needed (3) | Very Needed (4) | SUBTOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Employment |  |  |  |  |  |  |
| 1 | Help finding a job | 11 (11x0=0) | 15 (15x1=15) | 10 (10x2=20) | 23 (23x3=69) | 55 (55x4=220) | 0+15+20+69+220 = 324 |

Survey forms should be sorted by the county the respondent indicated on the Community Needs Survey form.  The agency should report the county level results in the Issue Area Tool.  The agency should consider summarizing results for each county, in addition to the overall survey results for all the completed surveys.

# Appendix 2 Organizing Community Forums

Source: RESULTS Educational Fund’s Activist Milestones

http://www.action.org/uploads/documents/How_to_Organize_a_Community_Forum.pdf

What is a community forum?

A community forum is an event that anyone can attend, where a panel of experts who have experience in a particular subject share their knowledge and perspectives and where members of the audience can ask questions during a pre-set time. It is a great resource for anyone who wants to learn more about an issue. It is also an excellent way to recruit activists.

Why hold a community forum?

Community forums can be a very effective way to raise awareness in your community and to get people involved in an issue. It can provide an opportunity for activists to join forces to demand action on a set of issues, advocate for change and get local media attention.

What would our community forum look like?

Much of the event depends the time and resources you have available to put into it. It can be as big or small as you want it, but in general, a community forum should last about an hour-- long enough to educate your audience and short enough to keep their attention. For example, the forum could have around three presenters, each speaking for 10–15 minutes. After all the presenters have spoken, there can be a question and answer session, lasting no more than 20 minutes. Finally, it can conclude with a 5–10 minute wrap-up session, motivating attendees and calling them to action.

- What is the most important thing you want to accomplish with this forum? Write this one down, because you will not want to forget it.

- Who can help, and how much time can each person commit? This should be a positive experience. Be realistic about the commitment each person is able to make so that the rest of the planning can go smoothly.

- Who can you collaborate with in the community? You probably do not have all the knowledge and resources to do everything yourself. There are already groups and advocates in your community who care about these issues and would want to be involved in this kind of event.

- What type of budget and resources do you have? You will need to know this before you secure a location, print handouts, plan refreshments, etc.

- Ideally, what would your forum look like? Spend some time dreaming up a forum that makes you happy and proud. What aspects or elements are most important to you?

Thinking about the Logistics

As with any event, it is hard to anticipate all logistical matters, but the better planning you do, the more smoothly the event will go. Use the following questions to help you brainstorm resources that are available and put your thoughts together for the event.

- When, where and at what time will the forum occur?

- How long should it last?

- How many people will speak and who should they be?

- Who will moderate?

- Will there be a sponsor for the event?

- How will we publicize the event?

- What will the room set up be?

- Will we need microphones or audio-visual equipment?

- Who can we collaborate with for this event?

- How will we notify the media about the event?

- Should we serve refreshments?

Assigning Tasks

Because there is a lot to do to make a community forum a success, you should ideally start planning the event at least eight to ten weeks in advance. Below is a suggestion of one way to divide the tasks. You may expand, contract, mix and match these fields of responsibility to match the size and personal interests in your team. One person may take on several of these roles, or many people may split them up further. The important thing is that all of these responsibilities are fulfilled and there is one point person overseeing the entire project.

If you are organizing a community forum on your own, then read through this section to see what you should be thinking about.

Team Leader Responsibilities:

- Keep the big picture in mind.

- Keep track of everyone's progress.

- Support each team member with their responsibilities when they need help.

- Manage budget.

Program Coordinator Responsibilities:

- Organize the actual program for the forum.

- Coordinate the agenda.

- Network with local organizations and advocates to find good speakers.

- Moderate the panel during the forum and help move the program along smoothly.

Site Organizer Responsibilities:

- Reserve the site and coordinate all the physical aspects of the event.

- Coordinate the banners, chairs, tables, handouts, sign in table, sound system, refreshments, etc.

Media Coordinator Responsibilities:

- Invite the media.

- Contact local newspapers and television and radio stations.  Follow up with them in the days and weeks leading up to the event.

- Write a press release.

- During the forum, be available to greet media professionals and provide them with materials.

- Publicity Coordinator Responsibilities:

- Build public awareness and "fill the room" for the forum.

- Invite people to the forum through public announcements and advertisements and in one-on-one contacts.

- Invite congressional representatives and local policy-makers.

Planning the Event

The Importance of Communication

Even if everyone is doing phenomenal work, planning a forum can turn chaotic if progress isn't communicated regularly. In many ways, hosting a community forum is like building a house. If everyone works on their own part of the house, without looking at the blueprint, you may have excellent components, staircases, windows, walls, but they will not fit together to make a house. Likewise, even if your community forum has great speakers, a nice venue and good refreshments, it will not go over well unless it fits into a greater plan.

Make sure that you have a system of communication worked out between teammates and keep your team leader updated on all progress so they can be on the look-out for any confusion or conflicting plans.

Setting a Date

Ideally, the community forum will take place during times when the issue you want to discuss is topical and relevant. This toolkit lays out a planning and preparation timeline of 5 to 6 weeks, but your team may choose to spend more or less time planning. Identify a space of days to aim for, and be prepared to adjust that date as you talk with your partner organizations, speakers, and the site.

Finding a Location

The location for your event will set the tone. Here are some things to think about:

- Will this place naturally draw an audience?

- Will there be any fee to use this space?

- What kind of atmosphere will best suit the forum you are planning? Are you looking for a small room, a large auditorium, a park, or the steps of your Parliament?

- Will the guests and the audience feel comfortable in the space? (For example, some people may not feel comfortable in a church building, others may need it to be handicap accessible, etc.)

- Is this a site that will be attractive to the media? (Is it easy to get to? Does it lend itself to good pictures?)

- Is the site accessible by public transportation? Is parking easily available?

Possible Locations:

- Community College or University

- Library

- Community Center

- Community Organization Meeting Room

- School

- Church, Synagogue, Temple or Mosque

- Town Square or Public Amphitheater

- City or State Government Building

Connecting with Community Partners

Partnering with community organizations that are interested in your issue will only enhance the success of your forum. Community partners can lend you help and support in getting materials, media coverage, and community attendance at the forum. Make a list of potential individuals and organizations you could partner with for the forum.

Calling potential partners:

        - Ask to speak with the director or other appropriate staff person.

- Introduce yourself.

- Ask if he or she has a moment to talk.

- Explain that you are planning a community forum.

- Ask if their organization would be interested in participating or if they can refer you to other interested parties or speakers.

- Set a plan to follow up — be sure to get all contact information.

- Thank them.

- Record contact information and follow up with referrals.

Setting the Agenda

Now it is time to plan the format of your forum. This sample agenda below should help you do this. The tone of the forum should be upbeat but serious and it should end positively, looking forward to future action.

- Welcome (5 minutes) Given by one of the organizers, local advocate or celebrity, probably the person who will act as moderator for the rest of the event

- Introduction (10 minutes)

- An overview of the issue to be discussed at the forum.

- Opening Remarks (10 minutes)

Publicity and Media

Getting Turnout at Your Event

Your event will have the greatest impact if as many people as possible attend. It is a good idea to have a plan on how you will get people to your event so that you do not spend a significant amount of time putting together an event and only have a small group of people attend. Keep in mind that the best strategy to get people to attend is to personally invite them.

Possible ways to increase turnout at your event:

- Make a list of the friends and family you will personally invite.

- Submit announcements to your local papers for events calendars.

- Hand out flyers at community events.

- Place flyers on bulletin boards at community centers, religious institutions, in coffee shops, music stores, bus stops, grocery stores, co-ops, laundromats, local schools and universities — anywhere there are people.

- Ask local newspapers and radio, and/or television stations to run public service announcements about the forum.

- Send invitation letters to all community organizations, groups, businesses, and individuals you want in attendance at the forum.

- If you will be having elected officials in attendance or a local celebrity giving the opening remarks, hype it!

Invite Elected Officials and Local Policy Makers

Inviting elected officials and local policy makers to your event is a great opportunity for them to spend time with constituents and hear about their concerns.

- Send a fax or e-mail to their office inviting them to attend your community forum.

- Explain what issue you will be discussing, why it is relevant to them, and why it is an important topic for their constituents.

- Let him or her know that you will honor them for attending and for previous good deeds.

- Note the date, time and location.

- Explain that he or she will offer part of the opening remarks (giving them a chance to express goodwill and concern for the community and the other speakers) and may choose to participate in the question and answer period.

- Inform him or her that you will be inviting the media to attend and ask about their availability to take questions from the media.

- A week after you have sent the fax, make a follow up phone call to their office scheduler.

- Once they have accepted your invitation go over the details of the event.

- Confirm the date, time and location.

- Explain the set-up of the event and who will be present.

- Discuss what you would like them to say at the event and when they will speak.

- Offer to send them talking points.

- A few days before the event, reconfirm their availability to attend.

Putting Together a Press Plan

You can do as many or as few of the following suggestions, based on the amount of time you have to put into getting media attention. Although it is up to you, keep in mind that the more media attention you get, the greater impact your forum will have.

- Try to get advance media coverage. Send a media advisory to key media contacts a week before the meeting.

- Consider inviting area college media classes to videotape your event.

- Make follow-up calls to media people, city desks, daybooks, and assignment editors a day or two before the meeting.

- Prepare a press packet for distribution to press people at the meeting. It should include a press release and background information on your issue and your organization.

- Prepare visuals. Both newspapers and television prefer taking interesting pictures rather than pictures of talking heads. Prepare some visuals, charts, banners, or stunts that you think might be interesting. The visual should not just be "catchy" but should convey your message.

- Talk with press people at the event. One person should be assigned as the spokesperson and to greet the press.

- Call the press people who did not come to tell them what happened, or send a follow-up press release if you do not expect to get much media coverage.

- Thank the press people for covering your event

- If you received inaccurate coverage, call the media contact to clarify your message.

- If the event was a success but media professionals were not present, publicize the results yourselves.

# Appendix 3 Conducting Focus Groups

Source: Community Tool Box

https://ctb.ku.edu/en/table-of-contents/assessment/assessing-community-needs-and-resources/conduct-focus-groups/main

Purpose of Using Focus a Group:  The purpose of conducting a focus group is to bring together a small number of individuals, approximately 10-15 persons, to have an in-depth discussion of the needs of the community and of the contributing factors related to the needs.

Steps to Plan a Focus Group:

- Select a team of staff and/or volunteers to plan the forum and conduct the forum.

- Identify who will serve as facilitator for the forum. The facilitator can be a manager or board member or volunteer from the community who has experience facilitating forums or focus groups.

- Identify the issues that will be focused on during the forum and the specific questions that will be asked.

- Identify a facility and date and time to conduct the event.

- Determine who to invite and assign someone to create and send the invitation or make calls to invite persons.  Invite persons that are best suited for this type of discussion and who will be able to contribute to an analytical discussion of barriers and needs.  Persons to invite may include agency volunteers, neighborhood council representatives, board members, community leaders, leaders of community service organizations/non-profit organizations, elected officials, educators, etc.

- Invite at least twice as many persons as you anticipate attending.  Call invited persons the day before the meeting to remind them.

- Determine how the discussion at the focus group will be documented or recorded during the event.

- Assign someone from your staff to provide a written summary report of the input from the focus group and set a timeline for developing and finalizing the summary report.

- Determine how the input from the focus group will be used in the community assessment process.

Possible Questions to Ask Focus Group:

1st Ask: Why does the identified need exist or what is causing the need?

2nd Once the group identifies the cause of a particular need, then delve deeper into it by asking why does the particular need exist?

3rd Continue discussing each issue and asking follow-up questions until the final root cause(s) has/have been identified.  These root causes may point to needs that may or may not be applicable to the community needs assessment.

Example of Discussion to Identify Underlying Needs/Root Causes

Below is an example of how a facilitator can help guide the focus group discussion in order to identify underlying needs.  The reason for going through this discussion is for the agency to determine the multiple needs that the agency and community should focus on addressing.  It may be helpful to use flip charts with sticky backs that can be hung on a wall during the meeting.

EXAMPLE: Condition or Need Identified by Group:  Persons cannot find a full-time job in the community.

Discuss why persons cannot find a full time job in the community by asking “What are some of the reasons persons can’t find a full-time job in the community?”  Then list the contributing factors.  Next, ask if there are any community assets or resources that could address the needs.  Finally, ask what solutions do they think can address the needs.

Example of three identified needs which have had the contributing factors identified through a series of progressive questions.  The Community Assets/Resources and Solutions have not been provided in this example.

| Identified Need | Contributing Factors | Community Assets/ Resources | Solutions |
| --- | --- | --- | --- |
| 1. Lack of Private Transportation | - inability to drive - high costs of car ownership - Why is there an inability to drive? - persons do not know how to drive - physical impairment - license revoked - What is causing the high costs of car ownership? - Lack of income - lack of credit - Unable to afford car insurance |  |  |
| 2. Lack of Public Transportation | a) Area government does not have a public transportation system b) No non-profits that have a transportation program |  |  |
| 3. Lack of Job Skills | - Persons can’t enroll in training programs required for the jobs available. a) Why can’t persons enroll in training programs for available jobs? - Persons lack the reading, writing, and math skills. - Lack of money to pay for training programs. - No training programs in the area. 1 - Why do persons lack the reading and math skills? Lack of high school diploma or GED. 2 - Why do persons have a lack of money to pay for training programs? (a) They don’t qualify for student financial aid. (b) Poor credit. (c) Low wages. - For the cause related to “no training programs in the area,” there is no need for the focus group to delve deeper into this condition. |  |  |

# Appendix 4 Root Cause Analysis

Source: Washington State Department of Enterprise Services

https://des.wa.gov/services/risk-management/about-risk-management/enterprise-risk-management/root-cause-analysis

Root Cause Analysis (RCA) is a popular and often-used technique that helps people answer the question of why the problem occurred in the first place. It seeks to identify the origin of a problem using a specific set of steps, with associated tools, to find the primary cause of the problem, so that you can:

- Determine what happened.

- Determine why it happened.

- Figure out what to do to reduce the likelihood that it will happen again.

RCA assumes that systems and events are interrelated. An action in one area triggers an action in another, and another, and so on. By tracing back these actions, you can discover where the problem started and how it grew into the symptom you're now facing.

You'll usually find three basic types of causes:

- Physical causes – Tangible, material items failed in some way (for example, a car's brakes stopped working).

- Human causes – People did something wrong, or did not do something that was needed. Human causes typically lead to physical causes (for example, no one filled the brake fluid, which led to the brakes failing).

- Organizational causes – A system, process, or policy that people use to make decisions or do their work is faulty (for example, no one person was responsible for vehicle maintenance, and everyone assumed someone else had filled the brake fluid).

RCA looks at all three types of causes. It involves investigating the patterns of negative effects, finding hidden flaws in the system, and discovering specific actions that contributed to the problem. This often means that RCA reveals more than one root cause.

You can apply RCA to almost any situation. Determining how far to go in your investigation requires good judgment and common sense. Theoretically, you could continue to trace root causes back to the Stone Age, but the effort would serve no useful purpose. Be careful to understand when you've found a significant cause that can, in fact, be changed.

The Root Cause Analysis Process

Step One: Define the Problem

- What do you see happening?

- What are the specific symptoms?

Step Two: Collect Data

- What proof do you have that the problem exists?

- How long has the problem existed?

- What is the impact of the problem?

You need to analyze a situation fully before you can move on to look at factors that contributed to the problem. To maximize the effectiveness of your RCA, get together everyone – experts and front line staff – who understands the situation. People who are most familiar with the problem can help lead you to a better understanding of the issues.

Step Three: Identify Possible Causal Factors

- What sequence of events leads to the problem?

- What conditions allow the problem to occur?

- What other problems surround the occurrence of the central problem?

During this stage, identify as many causal factors as possible. Too often, people identify one or two factors and then stop, but that's not sufficient. With RCA, you don't want to simply treat the most obvious causes – you want to dig deeper.

Step Four: Identify the Root Cause(s)

- Why does the causal factor exist?

- What is the real reason the problem occurred?

Use the same tools you used to identify the causal factors (in Step Three) to look at the roots of each factor. These tools are designed to encourage you to dig deeper at each level of cause and effect.

Step Five: Recommend and Implement Solutions

- What can you do to prevent the problem from happening again?

- How will the solution be implemented?

- Who will be responsible for it?

- What are the risks of implementing the solution?

Analyze your cause-and-effect process, and identify the changes needed for various systems. It's also important that you plan ahead to predict the effects of your solution. This way, you can spot potential failures before they happen.

Refer to the “But Why” appendix

# Appendix 5 But Why Technique

Source: Community Tool Box

https://ctb.ku.edu/en/table-of-contents/analyze/analyze-community-problems-and-solutions/root-causes/main

What are "root causes?"

Root causes are the basic reasons behind the problem or issue you are seeing in the community. Trying to figure out why the problem has developed is an essential part of the "problem solving process" in order to guarantee the right responses and also to help citizens "own" the problems.

What is the "but why?" technique?

The "But why?" technique is one method used to identify underlying causes of a community issue. These underlying factors are called "root causes."

The "But why?" technique examines a problem by asking questions to find out what caused it. Each time an answer is given, a follow-up "But why?" is asked.

For example, if you say that too many people in poor communities have problems with alcoholism, you should ask yourself "but why?" Once you come up with an answer to that question, probe the answer with another "but why?" question, until you reach the root of the problem, the root cause.

Why should you identify root causes?

Identifying genuine solutions to a problem means knowing what the real causes of the problem are. Taking action without identifying what factors contribute to the problem can result in misdirected efforts, and that wastes time and resources. However, by thoroughly studying the cause of the problem, you can build ownership, that is, by experiencing the problem you will understand it better, and be motivated to deal with it.

The "But why?" technique can be used to discover basic or "root" causes either in individuals or broader social systems:

1. It can be used to find which individual factors could provide targets of change for your cause, such as levels of knowledge, awareness, attitudes, and behavior.

- Do people need more knowledge about nutrition?

- Do children need to learn refusal skills to avoid smoking?

- Do teenagers need to learn how to use contraceptives?

2. It can explore social causes. For example, it could help us determine why a certain neighborhood seems to have a higher rate of a specific problem. These social causes divide into three main sub-groups:

- Cultural factors, such as customs, beliefs, and values;

- Economic factors, such as money, land, and resources;

- Political factors, such as decision-making power.

3. It can uncover multiple solutions for a certain problem and allow the user to see alternatives that he or she might not have seen before. It increases the chances of choosing the right solution, because many aspects of the problem are explored during the "But why?" exercise.

When should you identify root causes?

- Whenever you are faced with addressing a challenging community problem. Of course, the "But why?" technique is not always your best bet and should not be used 100% of the time. It's extremely efficient to find a variety of solutions and is a quick and inexpensive technique that can be done by anyone, at anytime, anywhere. For some issues, however, you should use more sophisticated methods, such as surveys, interviews and data collecting.

- When there is support for a "solution" that does not seem to get at the real causes of the problem. For example, if there is hunger in community, let's distribute free turkey at Thanksgiving.

- When there is ignorance or denial of why a community problem exists.

How does the "but why" technique work?

Technique Guide

Here's how it works. A group examines a community problem by asking what caused it. Each time someone gives an answer, the "asker" continues to probe, mostly by asking "But why?" or "How could that have been prevented." Example:

Problem:

Too many (too few) people are ________.

Q: But why? A. Because...

Q: But why? A. Because...

Q: Could that have been prevented? A. Yes

Q: How?

Q: But why? A. Because...

Q. But why? A. Because...

Q But why? (and so forth)

1. First, invite people who are both affected by the problem and are in a position to contribute to the solution (see Chapter 18, Section 3: Identifying Targets and agents of Change: Who Can Benefit and Who Can Help) to brainstorm possible causes. The more representative the working group is, the more likely it is for the root causes to be uncovered.

2. The working group should then examine a community problem, such as substance abuse or violence, by asking what caused it. Each time someone gives an answer, the group asks, "But why?" Here's an example:

Problem:

A child has an infected foot.

Q: But why? A. She stepped on broken glass while walking.

Q: Could that have been prevented? A. Yes.

Q: How? A. She could have been wearing shoes.

Q: But why doesn't the child have shoes? A. Because the family can't afford shoes.

Q. But why? A. The father or mother has no job.

Q. But why? (and so forth)

In this example, the "But why?" analysis leads to at least two very different conclusions. The criterion for choice between them is to look into the environment of each one. Many solutions may apply to your problem, so it's up to you to find the one that fits it better. The "But why?" analysis by itself doesn't lead automatically to the best solution. It just points out many paths you may take.

# Appendix 6 Outcomes and Outputs

While CAAs are held accountable for producing outcomes, they must also demonstrate they have the capacity to achieve their results through effective and efficient management and delivery of services.

We define outcomes or results as benefits to individuals, families, organizations, and communities. The outcomes are the changes that can be observed by following an agency service or intervention, which we call outputs.

Some agencies have problems identifying the difference between outcomes and outputs.

Outputs are the activities of the program which will produce data regarding the scope of the program.

Outputs are measured by such things as units of service, number of people served, number of households or families served, hours of participation or number of times in attendance at a program

Deciding which elements of the program are outputs and which are outcomes is important for both management and accountability.

On the following page you will find some examples of various elements of programs typically offered by Community Action Agencies. Please consider if these elements are outcomes or outputs.

According to the NonProfit Times :“An output details what your organization does, whereas an outcome defines changes that have taken place because of your organization’s work. Maybe people who participated in your organization’s programs learned to read, stopped smoking and started running, graduated from high school, or got a job. A solid description of outcomes tells the funder what change occurred, and how much change occurred over what period of time.”

Evaluationtoolkit.org state that OUTPUTS are the direct and measurable products of a program’s activities or services, often expressed in terms of units (hours, number of people or completed actions). In your logic model, outputs refer to the activities you will conduct and the people you hope to reach. OUTCOMES are the results or impact of these activities or services, often expressed in terms of an increase in understanding, and improvements in desired behaviors or attitudes of participants. In your logic model, outcomes refer to the short-term, mid-term, and long-term goals of your program.

Outputs don’t have to be numerical, they could be a program. They could be the number of volunteers you will recruit. They could be the number of food boxes you deliver, or the number of referrals you make. Each outcome should have measurable outputs.