## Sheet1
Due Date | Task | Status | Team Member Responsible | Other Team Members Involved
2025-07-01 | Review most recent WPNs and WAP Memos. Incorporate them into the manual as required. |  | TBD | TBD
2025-08-01 | Review most recent state memos and guidance. Incorporate them into the manual as required. |  | TBD | TBD
2025-08-01 | Share draft with subgrantees for initial review. |  | TBD | TBD
2025-10-01 | Review most recent WPNs and WAP Memos. Incorporate them into the manual as required. |  | TBD | TBD
2025-11-15 | Review most recent state memos and guidance. Incorporate them into the manual as required. |  | TBD | TBD
2026-01-07 | Review DOE Application Instructions and make inventory of likely changes for State Plan along with summary language to include in manual. |  | TBD | TBD
2026-01-15 | Review most recent WPNs and WAP Memos. Incorporate them into the manual as required. |  | TBD | TBD
2025-02-01 | Deadline for subgrantees for initial review. |  | TBD | TBD
2026-02-01 | Send out a survey to subgrantees and grantee staff to determine which areas of the manual, state memos, WPNs, and other guidance are most important for discussion during the subgrantee feedback meeting. |  | TBD | TBD
2026-02-15 | Review most recent state memos and guidance. Incorporate them into the manual as required. |  | TBD | TBD
2026-02-28 | Invite subgrantees to manual update meeting and provide them with a list of update areas you will be seeking input on. |  | TBD | TBD
2026-04-01 | Hold meeting with subgrantees to get input on update areas. Take notes and incorporate subgrantee feedback into manual. |  | TBD | TBD
2026-04-15 | Review most recent WPNs and WAP Memos. Incorporate them into the manual as required. |  | TBD | TBD
2026-05-01 | Review most recent state memos and guidance. Incorporate them into the manual as required. |  | TBD | TBD
2026-05-01 | Inventory final changes for new State Plan and incorporate them into the manual as required. |  | TBD | TBD
2026-05-01 | Share draft with subgrantees for final review. |  | TBD | TBD
2026-06-15 | Release final version of manual for subsequent program year. |  | TBD | TBD
2026-06-15 | Train grantee staff on new manual changes |  | TBD | TBD
2026-06-22 | Train subgrantee staff on new manual changes |  | TBD | TBD