## Template April 1- 2025 State Pl
April 1 2025 State Plan Template
Task | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Status / Comments
WAP State Plan Submission |  | 2024-09-02 | 2025-04-04
Pre-Planning Updates |  | 2024-09-02 | 2024-12-09
Update Operations and Policy Manuals |  | 2024-09-02 | 2024-09-27
Update T&TA Plans |  | 2024-09-30 | 2024-10-28
Update Monitoring Plans |  | 2024-11-01 | 2024-11-29
Update H&S Plans |  | 2024-12-02 | 2024-12-30
Update WRF |  | 2024-11-01 | 2024-11-29
Pre-Planning Office Prep
Note any staff changes |  | 2024-11-01 | 2024-11-29
Bring new staff up to date on roles and expectations |  | 2024-11-01 | 2024-11-29
Convene all task owners to review timeline |  | 2024-11-01 | 2024-11-29
Perform Risk Assessment on Subgrantees |  | 2024-12-02 | 2024-12-11
Hold meeting with Subgrantees for input into State Plan |  | 2024-11-01 | 2024-11-15
Review Carry-over projections |  | 2024-12-02 | 2024-12-12
Pull/Print SAMs and UEI on all Subgrantees |  | 2024-12-02 | 2024-12-12
DOE Release of WPN 25-1
Review WPN 25-1 for updates and additions |  | 2024-11-18 | 2024-11-29
Copy or Create NEW state plan in PAGE |  | 2024-11-18 | 2024-11-22
Begin Edits to State Plan
Mandatory Sections
Complete SF-424 & SF-424A |  | 2024-12-16 | 2024-12-19 |  |  | Use WPN 24-2 for Budget Planning; include language in public hearing notice that when WPN 25-2 is released the budget numbers will be modified.
Budget Justification |  | 2024-12-16 | 2024-12-27
Review and Approval of Budget |  | 2024-12-13 | 2025-01-03 |  |  | Recommend both internal review and DOE review
Provide budget for Subgrantee Contracts |  | 2025-01-06 | 2025-01-06 |  |  | Aim for Subgrantee contract execution to align with award start date of April 1
Annual File |  | 2024-12-16 | 2024-12-20
Master File |  | 2024-12-30 | 2025-01-06
Internal Review and Approval of DRAFT core state plan |  | 2025-01-06 | 2025-01-13 |  |  | The SF-424; SF 424A; Annual File and Master File are required for the public hearing
Notify DOE PO that state plan is ready for PRE-Review |  | 2025-01-13 | 2025-01-13
Required Attachments
Health and Safety Plan |  | 2025-01-13 | 2025-01-31 |  |  | If not included in Master File
T&TA Plan |  | 2025-01-13 | 2025-01-31 |  |  | If not included in Master File
QCI Inspection Form / Tech Monitoring Form |  | 2025-01-13 | 2025-01-31
Public Hearing Transcript & Notice with 10 days |  | 2025-01-13 | 2025-01-31
PAC Activity Documentation and Meeting Minutes |  | 2025-02-03 | 2025-02-05
Indirect Rate Agreement / Cost Allocation Plan |  | 2025-01-13 | 2025-01-31
Single Audit |  | 2025-01-13 | 2025-01-31
SF-Disclose of Lobbying Activities |  | 2025-01-13 | 2025-01-31
Admin / Fiscal Monitoring Instrument |  | 2025-01-13 | 2025-01-31
Budget / Subgrantee Allocations |  | 2025-01-13 | 2025-01-31 |  |  | Sometimes this is an excel file or .pdf
Draft State Plan and Publish for Review
Host PAC Meeting for review of state plan |  | 2025-01-13 | 2025-01-17
Generate presentation for PAC |  | 2015-01-13 | 2025-01-17
PAC Meeting Minutes |  | 2025-01-17 | 2025-01-20 |  |  | This is a required upload
Draft Public Hearing Notice
Publish DRAFT State Plan for Public Hearing |  | 2025-01-13 | 2025-01-13
Public Hearing Notice Approved |  | 2025-01-13 | 2025-01-13
Schedule Public Hearing, min 10 days notice |  | 2025-01-13 | 2025-01-13
Draft a formal transcript to read for Public Hearing |  | 2025-01-15 | 2025-01-31
Host Public Hearing |  | 2025-02-03 | 2025-02-03 |  |  | Can be done virtually or in-person
Review Public Hearing Comments |  | 2025-02-03 | 2025-02-03
Formal transcript for hearing |  | 2025-02-03 | 2025-02-03 |  |  | This is a required upload
Submit Plan to DOE |  | 2025-02-10 | 2025-02-10
Confirm all Required Uploads are in PAGE |  | 2025-02-07 | 2025-02-10 |  |  | We recommed submitting early
Notify DOE PO that plan is submitted |  | 2025-02-10 | 2025-02-10 |  |  | Due February 10 at noon
State Plan Approval Process
Set up DOE meeting for first review |  | 2025-02-17 | 2025-02-21 |  |  | Recommend setting up a formal meeting with DOE PO to review
Make revisions if needed |  | 2025-02-24 | 2025-02-26
DOE PO Team approval |  | 2025-03-03 | 2025-03-06
DOE CO Review- Golden |  | 2025-03-06 | 2025-03-19
Make revisions if needed |  | 2025-03-20 | 2025-03-25
DOE CO Approval - Golden |  | 2025-03-26 | 2025-03-28
DOE Approval on State Plan |  | 2025-03-31 | 2025-03-31
Read through grant agreement for terms and conditions - in FedConnect |  | 2025-03-31 | 2025-03-31
Accept the award in FedConnect |  | 2025-03-31 | 2025-03-31
Notify Subgrantees and Execute Contracts |  | 2025-04-01 | 2025-04-03 |  |  | Aim to execute Subgrantee Contracts on the Award Start Date