| Project phase 1: Planning, data collection, and beginning analyses |  | Due date | Cost | Can it be cut? |
| --- | --- | --- | --- | --- |
| Refine work and research plan. Gain approval by Association. Meeting with DPHHS/Association to determine content of addendums | 3 hours | Mid-January, 2025 | $375 | No |
| Meeting to review online design of survey and approve CNA lists of sections | 1.5 hours | Week of January 6-10, 2025 | $187.50 | No |
| Marketing, survey advertising, distribution, and engagement with HRDCs re: distribution | 20 hours |  | $2,500 | No |
| Marketing firm one-time fee |  |  | $500 | No |
| Association members share social media account information |  | By January 10, 2025 |  | No |
| Create and disseminate survey, manage data collection platform, and collect survey data | 15 hours | January 13-February 28, 2025 | $1,875 | No |
| HRDCs ask program partners if they would be interested in participating in focus groups |  | February, 2025 |  | No |
| Administration, scheduling, and facilitating 10 Zoom focus groups | 20 hours [(1 hour of scheduling + 1 hour of focus group)*10 = 20 hours) | February 3-March 21, 2025 | $2,500 | Yes* Individual agencies could complete |
| Focus group transcripts | 3 hours of admin + $750 for Rev.com transcripts | March 28 | $375 + $750 (10 transcripts*$75 = $750) = $1,125 | Yes* Individual agencies could complete |
| Survey data cleaning | 15 hours | March 14 | $1,875 | No |
| Creating individual datasets for CAAs (only if JG not doing analyses below) | 10 hours (1 hour per CAA *10 = 10 hours) | March 21 | $1,250 | Yes* if JG doing analysis below |
| TOTAL Phase 1 | 87.5 hours | March 25 | $12,187.50 or $10,937.50 if doing Phase 2 |  |
| Phase 2: Quantitative and qualitative data analysis |  | March 3 – May 9, 2025 |  | Yes |
| Statewide analysis/raw data tables creation | 15 hours | April 18 | $1,875 | No |
| 10 regional analyses/raw data tables creation | 150 hours (15 hours * 10 CAAs = 150 hours) | April 18 | $18,750 (or $1,875 each CAA) | No |
| Refining/designing tables, writing short descriptions of analyses | 150 hours (15 hours * 10 CAAs = 150 hours) | May 9 | $18,750 (or $1,875 each CAA) | Yes |
| Focus group coding/analysis | 40 hours (10 focus groups*4 hours | April 18 | $5,000 (or $500 each CAA) | Yes |
| Writing findings of focus group analysis | 50 hours (10 focus groups*5 hours) | May 9 | $6,250 (or $625 each CAA) | Yes |
| TOTAL Phase 2 | 405 hours | May 9 complete | $50,625 |  |
| Phase 3: CNA writing and review |  |  |  | Yes |
| Collecting secondary data/writing up section 1 | 315 hours (45 hours*7 CAAs) | January-April Complete April 25 | $39,375 for all 7 (or $5,625 each CAA) |  |
| Writing section 2s | 245 hours (35 hours*7 CAAs | May-August Complete August 22 | $30,625 for all 10 (or $4,375 each CAA) |  |
| Writing section 3s—If all CAAs provide administrative data to JG by end of February | 245 hours (35 hours*7 CAAs because focus group findings already complete) | March-May. Complete May 23 | $30,625 for all 10 (or $4,375 each CAA) |  |
| Writing section 4s | 175 hours (25 hours*7 CAAs) | August-September. Complete September 19 | $21,875 for all 7 (or $3,125 each CAA) |  |
| Writing 3 addendums (this is if JG does Phase 1 and 2, then this writing is shorter/easier/more cost effective) | 75 hours (25 hours *3) | June-August | $9,375 (or $3,125 each addendum) |  |
| Agencies review drafts of sections as complete sections with JG |  |  |  |  |
| CNA design and copyediting | 175 hours (25 hours*7 CAAs | Sept. 19-October 31 | $21,875 for all 7 (or $3,125 each CAA) |  |
| TOTAL Phase 3 | 1,230 hours | October 31 | $153,750 if JG doing writing of all 7 CNAs and 3 addendum $20,625 per CNA Phase 3 only. $3,175 per addendum Phase 3 only |  |
| TOTAL Phase 1: $12,187.50 (if JG just doing Phase 1) TOTAL Phase 1 and 2: $62,812.50 (analysis of each region can also be charged just per single CAA to reduce cost) TOTAL Phase 1, 2, and 3: $216,562.50f JG does all analysis and all writing of 7 CNAs and 3 addendums. JG can do just Phase 1, Phase 1 and 2, or all three Phases or write just some of the CNAs. |  |  |  |  |